# Please write the task t in the form of a spreadsheet in chronological order and in the form of a checklist.

# Please write the task t in the form of a spreadsheet in chronological order and in the form of a checklist.

Note: Due to model limitations, the response may not account for all data in the uploaded file(s). For better results, consider using fewer or smaller file(s) with essential excerpts. Learn more

# 📋 TURBOMINDZ NFT: COMPLETE PROJECT TASK LIST

## Chronological Checklist Format (Spreadsheet-Ready)

## HOW TO USE THIS DOCUMENT

Copy this into Google Sheets or Excel: 1. Copy the entire table 2. Paste into your spreadsheet 3. Use the checkbox column (☐) to track progress 4. Filter by Week, Phase, or Priority as needed

Priority Legend: - 🔴 = Critical (blocks other tasks) - 🟡 = Important (significantly impacts quality) - 🟢 = Nice to have (enhances but not essential)

Status Legend: - ☐ = Not Started - 🔄 = In Progress - ✅ = Complete - ⏸️ = On Hold - ❌ = Blocked

# PHASE 1: FOUNDATION (Weeks 1-8)

## Week 1: Planning & Legal

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 1.01 | Finalize project name | Confirm “Turbomindz” or select alternative; verify domain availability | 🔴 | 30 min | None | Decision required before proceeding |
| ☐ | 1.02 | Register domain | Purchase turbomindz.xyz or .com from Namecheap/GoDaddy | 🔴 | 15 min | 1.01 | ~$10-15/year |
| ☐ | 1.03 | Create project email accounts | Set up contact@, press@, team@ using Google Workspace or free provider | 🟡 | 20 min | 1.02 | Use domain email if possible |
| ☐ | 1.04 | Install MetaMask | Download and install MetaMask browser extension | 🔴 | 10 min | None | Use Chrome, Firefox, or Brave |
| ☐ | 1.05 | Create treasury wallet | Set up new MetaMask wallet for project treasury | 🔴 | 15 min | 1.04 | Never use personal wallet |
| ☐ | 1.06 | Secure seed phrase | Write 12-word seed phrase on paper, store securely | 🔴 | 10 min | 1.05 | NEVER store digitally |
| ☐ | 1.07 | Add Polygon network | Configure MetaMask to connect to Polygon mainnet | 🔴 | 10 min | 1.05 | RPC: https://polygon-rpc.com |
| ☐ | 1.08 | Fund wallet with MATIC | Purchase $20-50 MATIC via Coinbase or exchange | 🔴 | 20 min | 1.07 | For gas fees and minting |
| ☐ | 1.09 | Research quotes (batch 1) | Identify 50 verified public domain philosophical quotes | 🔴 | 2 hrs | None | Focus on diverse themes |
| ☐ | 1.10 | Research quotes (batch 2) | Identify 50 additional public domain quotes (100+ total) | 🔴 | 2 hrs | 1.09 | Variety of eras and traditions |
| ☐ | 1.11 | Verify public domain status | Confirm copyright status for all 100+ selected quotes | 🔴 | 1 hr | 1.10 | 70+ years since author death |
| ☐ | 1.12 | Organize quotes by theme | Categorize all quotes into 9 philosophical themes | 🔴 | 1 hr | 1.11 | Match forum architecture |
| ☐ | 1.13 | Create quote spreadsheet | Document quote, attribution, source, theme, PD verification | 🟡 | 30 min | 1.12 | Master reference document |
| ☐ | 1.14 | Draft Terms of Service | Create initial ToS using legal template | 🔴 | 2 hrs | None | Use Termly or similar |
| ☐ | 1.15 | Draft Privacy Policy | Create Privacy Policy compliant with GDPR/CCPA | 🔴 | 1 hr | None | Include cookie policy |
| ☐ | 1.16 | Research business structure | Determine if LLC/entity needed for jurisdiction | 🟡 | 1 hr | None | Consult local requirements |
| ☐ | 1.17 | Create documentation folder | Set up Google Drive/Notion for all project docs | 🟡 | 20 min | None | Organize by category |

Week 1 Subtotal: 17 tasks, ~12.5 hours

## Week 2: Brand & Identity

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 2.01 | Define color palette | Select primary (#0D7377), secondary (#D4AF37), accent colors | 🔴 | 30 min | None | Document hex codes |
| ☐ | 2.02 | Select typography | Choose headline (Playfair Display) and body (Inter) fonts | 🔴 | 30 min | None | Google Fonts = free |
| ☐ | 2.03 | Write brand voice guide | Document tone, vocabulary, do’s/don’ts | 🟡 | 1 hr | 2.01, 2.02 | Intellectual, creative, transparent |
| ☐ | 2.04 | Create mood board | Collect 15-20 visual references for aesthetic | 🟡 | 30 min | 2.01 | Pinterest or Figma |
| ☐ | 2.05 | Design logo (icon) | Create simple icon logo using Canva or AI | 🔴 | 1.5 hrs | 2.01, 2.02 | Must work at small sizes |
| ☐ | 2.06 | Design logo (wordmark) | Create full logo with “Turbomindz” text | 🔴 | 1 hr | 2.05 | Use brand fonts |
| ☐ | 2.07 | Create logo variations | Produce light/dark, various sizes, with/without text | 🟡 | 30 min | 2.06 | PNG + SVG formats |
| ☐ | 2.08 | Design profile picture | Create 400×400 social profile image | 🔴 | 30 min | 2.05 | Icon-focused, readable small |
| ☐ | 2.09 | Research competitors | Analyze 5 similar NFT/art marketplace projects | 🟡 | 2 hrs | None | Note strengths/weaknesses |
| ☐ | 2.10 | Document competitive analysis | Write findings, identify differentiation opportunities | 🟡 | 1 hr | 2.09 | What can we do better? |
| ☐ | 2.11 | Define marketplace categories | Finalize 10 art type categories with descriptions | 🔴 | 1 hr | None | Match user mental models |
| ☐ | 2.12 | Define theme room structure | Finalize 9 philosophical themes with subtopics | 🔴 | 1 hr | Week 1 quotes | Topics not authors |
| ☐ | 2.13 | Create thread tag system | Define [FS], [IC], [AUCTION], [SOLD], etc. with rules | 🔴 | 30 min | 2.11 | Standardize marketplace |
| ☐ | 2.14 | Write category descriptions | 1-2 sentences for each marketplace category | 🟡 | 1 hr | 2.11 | Help users know where to post |
| ☐ | 2.15 | Write theme descriptions | 1-2 sentences for each theme room | 🟡 | 1 hr | 2.12 | Explain scope of each |
| ☐ | 2.16 | Compile brand guidelines | Single document with all brand elements | 🟡 | 1 hr | 2.01-2.08 | Reference for all content |
| ☐ | 2.17 | Organize brand asset folder | Structure for logos, fonts, colors, templates | 🟡 | 20 min | 2.07 | Easy team access |

Week 2 Subtotal: 17 tasks, ~14.5 hours

## Week 3: AI Art Generation (Part 1)

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 3.01 | Subscribe to MidJourney | Sign up for MidJourney ($10-30/month) | 🔴 | 15 min | None | Basic plan sufficient |
| ☐ | 3.02 | Join MidJourney Discord | Access server for image generation | 🔴 | 10 min | 3.01 | Required for generation |
| ☐ | 3.03 | Learn MidJourney basics | Understand commands, parameters, workflows | 🔴 | 1 hr | 3.02 | Watch tutorials if needed |
| ☐ | 3.04 | Experiment with art style | Generate 20+ test images exploring aesthetics | 🔴 | 2 hrs | 3.03 | Find consistent look |
| ☐ | 3.05 | Define “Renaissance Digital” style | Document specific visual parameters that work | 🔴 | 30 min | 3.04 | Marble, gold, philosophical |
| ☐ | 3.06 | Create base prompt template | Write master prompt structure for consistency | 🔴 | 1 hr | 3.05 | Include all key elements |
| ☐ | 3.07 | Create theme-specific prompts | Adapt base prompt for each of 9 themes | 🔴 | 1 hr | 3.06, 2.12 | Color/mood variations |
| ☐ | 3.08 | Document prompt library | Save all working prompts organized by theme | 🟡 | 30 min | 3.07 | For future reference |
| ☐ | 3.09 | Assign quotes to artwork | Map 50 initial quotes to specific NFTs | 🔴 | 45 min | Week 1 quotes | Balance themes |
| ☐ | 3.10 | Generate artworks #1-10 | Create first batch using prompts | 🔴 | 2 hrs | 3.09 | Save best variations |
| ☐ | 3.11 | Generate artworks #11-20 | Create second batch | 🔴 | 2 hrs | 3.10 | Maintain consistency |
| ☐ | 3.12 | Generate artworks #21-25 | Create third batch | 🔴 | 1 hr | 3.11 | Quality over speed |
| ☐ | 3.13 | Quality check batch 1 | Review #1-25 for consistency, quality, readability | 🔴 | 1 hr | 3.12 | Use checklist |
| ☐ | 3.14 | Regenerate rejected images | Re-create any that don’t meet standards | 🟡 | 1 hr | 3.13 | May need multiple tries |
| ☐ | 3.15 | Organize approved images | Name files TM_001.png format, store in folder | 🟡 | 30 min | 3.14 | Consistent naming |

Week 3 Subtotal: 15 tasks, ~14.5 hours

## Week 4: AI Art Generation (Part 2) & IPFS Storage

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 4.01 | Generate artworks #26-35 | Create fourth batch | 🔴 | 2 hrs | Week 3 | Maintain style |
| ☐ | 4.02 | Generate artworks #36-45 | Create fifth batch | 🔴 | 2 hrs | 4.01 | Check theme balance |
| ☐ | 4.03 | Generate artworks #46-50 | Create final batch | 🔴 | 1 hr | 4.02 | Include rare pieces |
| ☐ | 4.04 | Quality check batch 2 | Review #26-50 for consistency | 🔴 | 1 hr | 4.03 | Compare to batch 1 |
| ☐ | 4.05 | Regenerate rejected images | Re-create any below standard | 🟡 | 1 hr | 4.04 | Perfectionism pays off |
| ☐ | 4.06 | Final QA all 50 images | Comprehensive review of complete collection | 🔴 | 1 hr | 4.05 | Full collection harmony |
| ☐ | 4.07 | Add quote text overlays | Add quote + attribution to each image | 🔴 | 3 hrs | 4.06 | Canva or Photoshop |
| ☐ | 4.08 | Export final images | High-res PNG, consistent dimensions | 🔴 | 30 min | 4.07 | 2000px+ recommended |
| ☐ | 4.09 | Create Pinata account | Sign up at pinata.cloud (free tier) | 🔴 | 15 min | None | IPFS storage |
| ☐ | 4.10 | Generate Pinata API key | Create API key for uploads | 🔴 | 10 min | 4.09 | Keep secure |
| ☐ | 4.11 | Upload all images to IPFS | Upload 50 final images, record CIDs | 🔴 | 1 hr | 4.08, 4.10 | Document each CID |
| ☐ | 4.12 | Create metadata JSON template | Build OpenSea-compatible structure | 🔴 | 30 min | None | Include all attributes |
| ☐ | 4.13 | Create 50 metadata files | Generate JSON for each NFT | 🔴 | 2 hrs | 4.11, 4.12 | Can script if technical |
| ☐ | 4.14 | Upload metadata to IPFS | Upload JSON files, record CIDs | 🔴 | 30 min | 4.13 | One folder recommended |
| ☐ | 4.15 | Create master CID spreadsheet | Document token#, image CID, metadata CID | 🟡 | 30 min | 4.14 | Critical reference |
| ☐ | 4.16 | Backup all files | Save copies of everything to backup location | 🔴 | 20 min | 4.15 | Multiple locations |

Week 4 Subtotal: 16 tasks, ~16.5 hours

## Week 5: OpenSea & Discord Setup

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 5.01 | Go to OpenSea | Navigate to opensea.io | 🔴 | 5 min | None | Use desktop browser |
| ☐ | 5.02 | Connect wallet | Connect MetaMask treasury wallet | 🔴 | 10 min | Week 1 wallet | Verify correct wallet |
| ☐ | 5.03 | Switch to Polygon | Select Polygon network in OpenSea | 🔴 | 5 min | 5.02 | Lower fees |
| ☐ | 5.04 | Create collection | Set up “Turbomindz” collection | 🔴 | 20 min | 5.03 | Unique URL slug |
| ☐ | 5.05 | Write collection description | Compelling description with links | 🔴 | 30 min | 5.04 | Include Discord, website |
| ☐ | 5.06 | Set collection royalties | Configure 5% creator royalty | 🔴 | 10 min | 5.04 | Treasury wallet address |
| ☐ | 5.07 | Set collection category | Select “Art” category | 🔴 | 5 min | 5.04 | Best fit |
| ☐ | 5.08 | Upload collection logo | Add 350×350 logo image | 🔴 | 10 min | 5.04, Week 2 | Brand logo |
| ☐ | 5.09 | Upload collection banner | Add 1400×400 banner image | 🔴 | 10 min | 5.04 | Create if not done |
| ☐ | 5.10 | Configure social links | Add Twitter, Discord, website URLs | 🟡 | 10 min | 5.04 | After accounts created |
| ☐ | 5.11 | Mint 5 test NFTs | Create test items to verify process | 🔴 | 30 min | Week 4 CIDs | Don’t list for sale |
| ☐ | 5.12 | Verify test NFTs display | Check images, metadata, attributes | 🔴 | 15 min | 5.11 | Troubleshoot issues |
| ☐ | 5.13 | Test private sale | Create private listing for test | 🔴 | 30 min | 5.11 | Verify workflow |
| ☐ | 5.14 | Document OpenSea workflow | Write step-by-step for reference | 🟡 | 30 min | 5.13 | For future minting |
| ☐ | 5.15 | Create Discord server | Set up new server for Turbomindz | 🔴 | 15 min | None | Use desktop app |
| ☐ | 5.16 | Configure server settings | Name, icon, region | 🔴 | 10 min | 5.15 | Add brand logo |
| ☐ | 5.17 | Enable Community features | Turn on in Server Settings | 🔴 | 10 min | 5.16 | Required for forums |
| ☐ | 5.18 | Enable Forum Channels | Activate Forum Channel feature | 🔴 | 10 min | 5.17 | Core feature |
| ☐ | 5.19 | Create Information category | #welcome, #rules-and-charter, #announcements | 🔴 | 20 min | 5.18 | Read-only channels |
| ☐ | 5.20 | Create Marketplace: Paintings | #paintings-drawings forum channel | 🔴 | 10 min | 5.18 | First category |
| ☐ | 5.21 | Create Marketplace: Sculpture | #sculpture-3d forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.22 | Create Marketplace: Digital | #digital-generative forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.23 | Create Marketplace: Photography | #photography-editions forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.24 | Create Marketplace: Prints | #prints-multiples forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.25 | Create Marketplace: Books | #books-zines-manuscripts forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.26 | Create Marketplace: Craft | #craft-design-wearables forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.27 | Create Marketplace: Calligraphy | #calligraphy-lettering-type forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.28 | Create Marketplace: Commissions | #commissions-collaborations forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.29 | Create Marketplace: Services | #services-studio-support forum channel | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.30 | Create Registry category | #registry-how-to, #marriage-requests, #verified-marriages, #completed-deals | 🔴 | 30 min | 5.18 | Marriage system |
| ☐ | 5.31 | Create Themes: Classical | #classical-foundations discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.32 | Create Themes: Enlightenment | #enlightenment-reason discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.33 | Create Themes: Existentialism | #existentialism-modern discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.34 | Create Themes: Mysticism | #mysticism-esoterica discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.35 | Create Themes: Eastern | #eastern-wisdom discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.36 | Create Themes: Science | #science-media-modernity discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.37 | Create Themes: Poetry | #poetry-aesthetics-literature discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.38 | Create Themes: Civic | #civic-social-moral discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.39 | Create Themes: Psychology | #psychology-mind-meaning discussion | 🔴 | 10 min | 5.18 |  |
| ☐ | 5.40 | Create Education category | #critique, #tools-tech, #legal-ip, #success-mindset, #introductions | 🔴 | 30 min | 5.18 |  |
| ☐ | 5.41 | Create Support category | #help-questions, #technical-support, #report-issues | 🔴 | 15 min | 5.18 |  |
| ☐ | 5.42 | Create Governance category | #proposals, #voting, #tribunal, #transparency | 🔴 | 20 min | 5.18 |  |
| ☐ | 5.43 | Add [FS] tag to marketplaces | “For Sale” tag on all marketplace forums | 🔴 | 10 min | 5.20-5.29 |  |
| ☐ | 5.44 | Add [IC] tag to marketplaces | “Interest Check” tag | 🔴 | 10 min | 5.20-5.29 |  |
| ☐ | 5.45 | Add [AUCTION] tag | “Auction” tag | 🔴 | 10 min | 5.20-5.29 |  |
| ☐ | 5.46 | Add [SOLD] tag | “Sold” tag | 🔴 | 10 min | 5.20-5.29 |  |
| ☐ | 5.47 | Add [WTB/WTT] tag | “Want to Buy/Trade” tag | 🔴 | 10 min | 5.20-5.29 |  |
| ☐ | 5.48 | Add [PROVENANCE] tag | “Provenance” tag | 🟡 | 10 min | 5.20-5.29 |  |
| ☐ | 5.49 | Add [COA] tag | “Certificate of Authenticity” tag | 🟡 | 10 min | 5.20-5.29 |  |
| ☐ | 5.50 | Add [SHIPPING] tag | “Shipping” tag | 🟡 | 10 min | 5.20-5.29 |  |

Week 5 Subtotal: 50 tasks, ~10 hours

## Week 6: Roles, Token Gating & Governance

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 6.01 | Create @Visitor role | Default role for non-holders | 🔴 | 10 min | Week 5 Discord | Limited access |
| ☐ | 6.02 | Create @Member role | NFT holder role | 🔴 | 10 min | 6.01 | Full access |
| ☐ | 6.03 | Create @Trusted Seller role | 5+ trades, 0 disputes badge | 🟡 | 10 min | 6.02 | Prestige |
| ☐ | 6.04 | Create @Scribe role | Moderator/verifier role | 🔴 | 10 min | 6.02 | Elevated permissions |
| ☐ | 6.05 | Create @Elder role | Dispute panel eligible | 🔴 | 10 min | 6.02 |  |
| ☐ | 6.06 | Create @Founder role | Admin role | 🔴 | 10 min | 6.02 | Highest permissions |
| ☐ | 6.07 | Assign role colors | Distinct colors for each role | 🟡 | 15 min | 6.01-6.06 | Visual hierarchy |
| ☐ | 6.08 | Set @Visitor permissions | Public channels only | 🔴 | 15 min | 6.01 | Information category |
| ☐ | 6.09 | Set @Member permissions | All token-gated channels | 🔴 | 20 min | 6.02 | Marketplace + Themes |
| ☐ | 6.10 | Set @Scribe permissions | Moderation capabilities | 🔴 | 15 min | 6.04 | Manage messages, pins |
| ☐ | 6.11 | Set @Elder permissions | Governance access | 🔴 | 10 min | 6.05 | Tribunal channels |
| ☐ | 6.12 | Set @Founder permissions | Full admin | 🔴 | 10 min | 6.06 | All permissions |
| ☐ | 6.13 | Write welcome message | Auto-message for new joins | 🟡 | 20 min | 6.01 | Include verification link |
| ☐ | 6.14 | Create rules embed | Formatted rules in #rules-and-charter | 🔴 | 30 min | Week 5 | Clear, readable |
| ☐ | 6.15 | Create Guild.xyz account | Sign up at guild.xyz | 🔴 | 15 min | None | Free |
| ☐ | 6.16 | Create Turbomindz Guild | Set up new guild for project | 🔴 | 15 min | 6.15 |  |
| ☐ | 6.17 | Connect Discord to Guild | Link server to Guild.xyz | 🔴 | 15 min | 6.16, Week 5 | Follow prompts |
| ☐ | 6.18 | Get OpenSea contract address | Find collection contract from OpenSea | 🔴 | 10 min | Week 5 | In collection details |
| ☐ | 6.19 | Configure @Member requirement | 1+ Turbomindz NFT = @Member role | 🔴 | 20 min | 6.17, 6.18 | Chain: Polygon |
| ☐ | 6.20 | Configure @Trusted Seller | Optional: Trade count requirement | 🟡 | 20 min | 6.19 | May need manual |
| ☐ | 6.21 | Create verify button/channel | Add verification entry point | 🔴 | 15 min | 6.19 | #welcome or #verify |
| ☐ | 6.22 | Test verification (self) | Verify using test NFT | 🔴 | 15 min | 6.21 | End-to-end test |
| ☐ | 6.23 | Test verification (other) | Have someone else test | 🔴 | 15 min | 6.22 | Confirm works for others |
| ☐ | 6.24 | Document verification process | Write user guide | 🟡 | 20 min | 6.23 | For FAQ/help |
| ☐ | 6.25 | Create Snapshot account | Sign up at snapshot.org | 🔴 | 15 min | None | Connect wallet |
| ☐ | 6.26 | Create Snapshot space | Set up “Turbomindz” space | 🔴 | 20 min | 6.25 |  |
| ☐ | 6.27 | Configure voting strategy | erc721-balance-of for NFT voting | 🟡 | 15 min | 6.26 | 1 NFT = 1 vote |
| ☐ | 6.28 | Add collection contract | Link OpenSea contract to Snapshot | 🔴 | 10 min | 6.18, 6.26 | Network: Polygon |
| ☐ | 6.29 | Set voting parameters | Duration, quorum settings | 🟡 | 15 min | 6.27 | 7 days, 10% quorum |
| ☐ | 6.30 | Create test proposal | Run test vote to verify | 🟡 | 20 min | 6.29 | Delete after |
| ☐ | 6.31 | Document integrations | Reference doc for Guild + Snapshot setup | 🟡 | 30 min | 6.24, 6.30 | Troubleshooting |

Week 6 Subtotal: 31 tasks, ~7.5 hours

## Week 7: Documentation & Charter

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 7.01 | Write Charter Preamble | Opening statement, mission, values | 🔴 | 30 min | None | Set the tone |
| ☐ | 7.02 | Write Article I: Marriage Pact | Photo/video requirements, verification, permanence | 🔴 | 1 hr | None | Core mechanic |
| ☐ | 7.03 | Write Article II: Open Market | Public negotiation, tag requirements, listing format | 🔴 | 1 hr | Week 2 tags | Reference tag system |
| ☐ | 7.04 | Write Article III: Shipping | Seller/buyer obligations, packing by art type | 🔴 | 45 min | 2.11 | Category-specific |
| ☐ | 7.05 | Write Article IV: Tribunal | Elder selection, evidence, deliberation, remedies | 🔴 | 45 min | None | Dispute process |
| ☐ | 7.06 | Write Article V: Governance | Proposals, voting, thresholds, implementation | 🔴 | 30 min | Week 6 Snapshot | Match config |
| ☐ | 7.07 | Write Article VI: Enforcement | Strikes, suspension, exile process | 🔴 | 30 min | None | Consequences |
| ☐ | 7.08 | Write Article VII: Roles | Requirements and responsibilities for each role | 🔴 | 30 min | Week 6 roles | Match role setup |
| ☐ | 7.09 | Write Article VIII: Content/IP | Theme room guidelines, public domain rules | 🔴 | 30 min | None | Legal protection |
| ☐ | 7.10 | Write Article IX: Disclaimers | Platform as venue, liability limits | 🔴 | 30 min | Week 1 legal | Standard disclaimers |
| ☐ | 7.11 | Review Charter completeness | Ensure all articles complete and consistent | 🔴 | 30 min | 7.01-7.10 | Check cross-references |
| ☐ | 7.12 | Create Marriage SOP | Step-by-step verification guide for Scribes | 🔴 | 45 min | 7.02 | Include checklist |
| ☐ | 7.13 | Create Trading SOP | Step-by-step trading guide with tag usage | 🔴 | 45 min | 7.03 | Include examples |
| ☐ | 7.14 | Create Shipping Standards | Packing requirements by art type | 🔴 | 45 min | 7.04 | Visual examples help |
| ☐ | 7.15 | Create Dispute Flowchart | Visual process diagram | 🔴 | 45 min | 7.05 | Figma or Canva |
| ☐ | 7.16 | Write FAQ (batch 1) | Questions 1-15 | 🔴 | 1 hr | 7.01-7.10 | Most common Qs |
| ☐ | 7.17 | Write FAQ (batch 2) | Questions 16-30 | 🔴 | 1 hr | 7.16 | Detailed Qs |
| ☐ | 7.18 | Create Quick Start guide | 1-page new user guide | 🟡 | 30 min | 7.16 | Simple steps |
| ☐ | 7.19 | Create Detailed User guide | Comprehensive guide | 🟡 | 1 hr | 7.17 | All processes |
| ☐ | 7.20 | Format Charter for Discord | Clean embed format | 🔴 | 30 min | 7.11 | Readable in Discord |
| ☐ | 7.21 | Post Charter to Discord | Pin in #rules-and-charter | 🔴 | 15 min | 7.20 | Official publication |
| ☐ | 7.22 | Create public Charter link | Google Doc or Notion page | 🟡 | 20 min | 7.11 | For website |
| ☐ | 7.23 | Post SOPs to Discord | Pin in appropriate channels | 🟡 | 15 min | 7.12-7.14 | Reference documents |

Week 7 Subtotal: 23 tasks, ~14 hours

## Week 8: Team Building & Testing

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 8.01 | List Scribe candidates | Identify 5-10 potential moderators | 🔴 | 1 hr | None | Existing networks |
| ☐ | 8.02 | Research candidates | Check their online presence, reputation | 🟡 | 1 hr | 8.01 | Trustworthiness |
| ☐ | 8.03 | Draft outreach message | Template for reaching out | 🟡 | 20 min | 8.01 | Professional |
| ☐ | 8.04 | Reach out to candidates | Send messages to top 5-7 | 🔴 | 1 hr | 8.03 | Personalize each |
| ☐ | 8.05 | Schedule interviews | Set up calls with interested parties | 🔴 | 30 min | 8.04 | Flexible timing |
| ☐ | 8.06 | Conduct interviews | Video/voice calls (15-30 min each) | 🔴 | 2 hrs | 8.05 | 4-5 interviews |
| ☐ | 8.07 | Select first Scribes | Choose 2-3 initial Scribes | 🔴 | 30 min | 8.06 | Quality over quantity |
| ☐ | 8.08 | Send acceptance messages | Confirm selected Scribes | 🔴 | 15 min | 8.07 | Welcome them |
| ☐ | 8.09 | Grant Scribe roles | Assign @Scribe in Discord | 🔴 | 10 min | 8.08 |  |
| ☐ | 8.10 | Share documentation | Give Scribes access to SOPs, Charter | 🔴 | 15 min | 8.09, Week 7 | Google Drive or Notion |
| ☐ | 8.11 | Schedule training session | Set time for Scribe training | 🔴 | 10 min | 8.09 | Video call |
| ☐ | 8.12 | Train on Marriage process | Walk through SOP step by step | 🔴 | 1 hr | 8.11 | Screen share |
| ☐ | 8.13 | Train on Trading process | Walk through marketplace moderation | 🔴 | 45 min | 8.12 | Tag enforcement |
| ☐ | 8.14 | Train on tag management | Explain tag system, common issues | 🔴 | 30 min | 8.13 | Practical examples |
| ☐ | 8.15 | Train on moderation tools | Discord moderation features | 🟡 | 30 min | 8.14 | Timeout, delete, warn |
| ☐ | 8.16 | Answer Scribe questions | Open Q&A session | 🟡 | 30 min | 8.15 | Address concerns |
| ☐ | 8.17 | Create test Marriage request | Team member posts mock request | 🔴 | 30 min | 8.12 | Realistic |
| ☐ | 8.18 | Process test Marriage | Scribe verifies mock request | 🔴 | 30 min | 8.17 | Full workflow |
| ☐ | 8.19 | Review Marriage test | Assess process, identify issues | 🔴 | 15 min | 8.18 | Debrief |
| ☐ | 8.20 | Create test sale listing | Post mock [FS] listing | 🔴 | 20 min | 8.13 | With tags |
| ☐ | 8.21 | Run test negotiation | Mock offer/counter-offer | 🔴 | 30 min | 8.20 | Realistic dialogue |
| ☐ | 8.22 | Complete test private sale | OpenSea private sale test | 🔴 | 20 min | 8.21 | Between wallets |
| ☐ | 8.23 | Test shipping documentation | Mock tracking/packing posts | 🟡 | 15 min | 8.22 | Template |
| ☐ | 8.24 | Review Trading test | Assess process, identify issues | 🔴 | 15 min | 8.23 | Debrief |
| ☐ | 8.25 | Run mock Dispute | Test dispute process | 🟡 | 45 min | 8.24 | Elder simulation |
| ☐ | 8.26 | Document test results | Record all issues found | 🟡 | 30 min | 8.19, 8.24, 8.25 | Track fixes needed |
| ☐ | 8.27 | Fix identified issues | Address problems from testing | 🔴 | 1 hr | 8.26 | Iterate |
| ☐ | 8.28 | Re-test fixed issues | Verify fixes work | 🔴 | 30 min | 8.27 | Confirmation |
| ☐ | 8.29 | Create Scribe handbook | Compiled training + guidelines | 🟡 | 1 hr | 8.12-8.16 | Reference doc |
| ☐ | 8.30 | Phase 1 review meeting | Team call to verify completion | 🔴 | 1 hr | All above | Checklist review |

Week 8 Subtotal: 30 tasks, ~17.5 hours

# PHASE 2: PRE-LAUNCH MARKETING (Weeks 9-12)

## Week 9: Website Build

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 9.01 | Sign up for Carrd | Create account at carrd.co | 🔴 | 10 min | None |  |
| ☐ | 9.02 | Upgrade to Carrd Pro | Pay $19/year for Pro features | 🔴 | 5 min | 9.01 | Custom domain, forms |
| ☐ | 9.03 | Select blank template | Start fresh for custom design | 🔴 | 5 min | 9.02 |  |
| ☐ | 9.04 | Set page background | Apply brand colors | 🔴 | 10 min | 9.03 | Consistent look |
| ☐ | 9.05 | Build Hero: Background | Add background image or gradient | 🔴 | 15 min | 9.04 | Eye-catching |
| ☐ | 9.06 | Build Hero: Headline | Add main headline text | 🔴 | 15 min | 9.05 | “Where Wisdom Meets Canvas” |
| ☐ | 9.07 | Build Hero: Subheadline | Add supporting text | 🔴 | 15 min | 9.06 | Value proposition |
| ☐ | 9.08 | Build Hero: Primary CTA | “Enter Turbomindz” button → Discord | 🔴 | 10 min | 9.07 | Main action |
| ☐ | 9.09 | Build Hero: Secondary CTA | “View Collection” button → OpenSea | 🔴 | 10 min | 9.08 | Secondary action |
| ☐ | 9.10 | Build How It Works: Header | Section title | 🔴 | 10 min | 9.09 |  |
| ☐ | 9.11 | Build How It Works: Step 1 | Collect - icon + text | 🔴 | 15 min | 9.10 |  |
| ☐ | 9.12 | Build How It Works: Step 2 | Marry - icon + text | 🔴 | 15 min | 9.11 |  |
| ☐ | 9.13 | Build How It Works: Step 3 | Trade - icon + text | 🔴 | 15 min | 9.12 |  |
| ☐ | 9.14 | Build Marketplace preview | 10 category icons/names | 🔴 | 30 min | 9.13 | Grid layout |
| ☐ | 9.15 | Build Themes preview | 9 theme icons/names | 🔴 | 30 min | 9.14 | Grid layout |
| ☐ | 9.16 | Build Registry section | Marriage explanation | 🟡 | 20 min | 9.15 | Brief overview |
| ☐ | 9.17 | Build Honor System section | Governance explanation | 🟡 | 20 min | 9.16 | Trust + transparency |
| ☐ | 9.18 | Build Manifesto section | About us / mission | 🟡 | 20 min | 9.17 | Brand story |
| ☐ | 9.19 | Build FAQ: Question 1 | What do I own? | 🔴 | 10 min | 9.18 | Accordion |
| ☐ | 9.20 | Build FAQ: Question 2 | How does marketplace work? | 🔴 | 10 min | 9.19 |  |
| ☐ | 9.21 | Build FAQ: Question 3 | How does Marriage work? | 🔴 | 10 min | 9.20 |  |
| ☐ | 9.22 | Build FAQ: Question 4 | What are thread tags? | 🔴 | 10 min | 9.21 |  |
| ☐ | 9.23 | Build FAQ: Question 5 | What if something goes wrong? | 🔴 | 10 min | 9.22 |  |
| ☐ | 9.24 | Build FAQ: Question 6 | Why topics not authors? | 🔴 | 10 min | 9.23 |  |
| ☐ | 9.25 | Build Footer: Social links | Discord, Twitter, OpenSea | 🔴 | 15 min | 9.24 | Icons preferred |
| ☐ | 9.26 | Build Footer: Legal links | ToS, Privacy | 🔴 | 10 min | 9.25 | Link to docs |
| ☐ | 9.27 | Build Footer: Copyright | © 2025 Turbomindz | 🔴 | 5 min | 9.26 |  |
| ☐ | 9.28 | Add internal anchor links | Smooth scroll navigation | 🟡 | 15 min | All above | Better UX |
| ☐ | 9.29 | Connect custom domain | Point turbomindz.xyz to Carrd | 🔴 | 20 min | Week 1 domain | DNS settings |
| ☐ | 9.30 | Configure SSL | Enable HTTPS | 🔴 | 10 min | 9.29 | Usually automatic |
| ☐ | 9.31 | Test desktop view | Check all sections on desktop | 🔴 | 15 min | 9.30 |  |
| ☐ | 9.32 | Test mobile view | Check responsive on mobile | 🔴 | 15 min | 9.31 | Critical |
| ☐ | 9.33 | Test tablet view | Check responsive on tablet | 🟡 | 10 min | 9.32 |  |
| ☐ | 9.34 | Test page speed | Verify <3 second load | 🟡 | 10 min | 9.33 | PageSpeed Insights |
| ☐ | 9.35 | Fix any display issues | Address problems found | 🔴 | 30 min | 9.31-9.33 | Iterate |
| ☐ | 9.36 | Publish site | Make live | 🔴 | 5 min | 9.35 | Go! |

Week 9 Subtotal: 36 tasks, ~8 hours

## Week 10: Content & Design Assets

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 10.01 | Write Hero headline (final) | Polish main headline | 🔴 | 15 min | Week 9 | Compelling |
| ☐ | 10.02 | Write Hero subheadline (final) | Polish supporting text | 🔴 | 15 min | 10.01 | Value prop |
| ☐ | 10.03 | Write How It Works copy | Final text for 3 steps | 🔴 | 30 min | Week 9 | Concise |
| ☐ | 10.04 | Write Marketplace copy | Intro text for categories | 🔴 | 20 min | Week 9 |  |
| ☐ | 10.05 | Write Themes copy | Intro text for theme rooms | 🔴 | 20 min | Week 9 |  |
| ☐ | 10.06 | Write Registry copy | Marriage explanation | 🔴 | 20 min | Week 9 |  |
| ☐ | 10.07 | Write Honor System copy | Governance explanation | 🔴 | 20 min | Week 9 |  |
| ☐ | 10.08 | Write Manifesto | Full about us / mission | 🔴 | 45 min | Week 9 | Brand story |
| ☐ | 10.09 | Write all FAQ answers | Final versions | 🔴 | 45 min | Week 9 | Clear, helpful |
| ☐ | 10.10 | Proofread all copy | Check spelling, grammar, consistency | 🔴 | 30 min | 10.01-10.09 | Fresh eyes help |
| ☐ | 10.11 | Update website with final copy | Replace placeholder text | 🔴 | 30 min | 10.10 |  |
| ☐ | 10.12 | Create OpenSea banner | 1400×400 branded image | 🔴 | 45 min | Week 2 brand | Canva |
| ☐ | 10.13 | Create Discord banner | 960×540 server banner | 🔴 | 45 min | 10.12 | Adapt design |
| ☐ | 10.14 | Create Twitter header | 1500×500 profile header | 🔴 | 30 min | 10.12 |  |
| ☐ | 10.15 | Design “Verified Marriage” stamp | Gold seal PNG | 🔴 | 45 min | None | For registry |
| ☐ | 10.16 | Create social template 1 | Quote post template | 🔴 | 20 min | Week 2 | Canva |
| ☐ | 10.17 | Create social template 2 | Announcement template | 🔴 | 20 min | 10.16 |  |
| ☐ | 10.18 | Create social template 3 | Feature/highlight template | 🔴 | 20 min | 10.17 |  |
| ☐ | 10.19 | Create social template 4 | Stats/metrics template | 🟡 | 20 min | 10.18 |  |
| ☐ | 10.20 | Create social template 5 | Q&A/FAQ template | 🟡 | 20 min | 10.19 |  |
| ☐ | 10.21 | Create social template 6 | Member spotlight template | 🟡 | 20 min | 10.20 |  |
| ☐ | 10.22 | Create social template 7 | Trade story template | 🟡 | 20 min | 10.21 |  |
| ☐ | 10.23 | Create social template 8 | Philosophy challenge template | 🟡 | 20 min | 10.22 |  |
| ☐ | 10.24 | Create social template 9 | Countdown template | 🟡 | 20 min | 10.23 |  |
| ☐ | 10.25 | Create social template 10 | Generic branded template | 🟡 | 20 min | 10.24 |  |
| ☐ | 10.26 | Create quote card template | 1080×1080 for quotes | 🟡 | 30 min | 10.16 | Theme rooms |
| ☐ | 10.27 | Design category icon 1-5 | First 5 marketplace icons | 🟡 | 45 min | Week 2 | 256×256 |
| ☐ | 10.28 | Design category icon 6-10 | Remaining marketplace icons | 🟡 | 45 min | 10.27 |  |
| ☐ | 10.29 | Design theme icon 1-5 | First 5 theme icons | 🟡 | 40 min | Week 2 |  |
| ☐ | 10.30 | Design theme icon 6-9 | Remaining theme icons | 🟡 | 30 min | 10.29 |  |
| ☐ | 10.31 | Design role badges | Member, Trusted, Scribe, Elder, Founder | 🟡 | 40 min | Week 2 | 128×128 |
| ☐ | 10.32 | Upload OpenSea banner | Apply to collection | 🔴 | 10 min | 10.12 |  |
| ☐ | 10.33 | Upload Discord banner | Apply to server | 🔴 | 10 min | 10.13 |  |
| ☐ | 10.34 | Set up Google Analytics | Create property, add to site | 🟡 | 20 min | Week 9 site | Basic tracking |
| ☐ | 10.35 | Create press kit folder | Google Drive shared folder | 🟡 | 15 min | None |  |
| ☐ | 10.36 | Add logos to press kit | All logo versions | 🟡 | 10 min | 10.35 | High-res |
| ☐ | 10.37 | Add screenshots to press kit | OpenSea, Discord, website | 🟡 | 15 min | 10.36 |  |
| ☐ | 10.38 | Write press kit one-pager | 1-page project overview | 🟡 | 45 min | 10.37 | PDF format |
| ☐ | 10.39 | Write founder bio | Short bio for press | 🟡 | 20 min | 10.38 |  |
| ☐ | 10.40 | Compile final press kit | Organize all materials | 🟡 | 15 min | 10.35-10.39 | Ready to share |

Week 10 Subtotal: 40 tasks, ~14.5 hours

## Week 11: Social Media Launch

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 11.01 | Create Twitter account | @turbomindz or similar | 🔴 | 15 min | None | Verify email |
| ☐ | 11.02 | Set Twitter profile picture | Upload logo | 🔴 | 5 min | 11.01, Week 2 |  |
| ☐ | 11.03 | Set Twitter header | Upload banner | 🔴 | 5 min | 11.02, 10.14 |  |
| ☐ | 11.04 | Write Twitter bio | Compelling 160 chars | 🔴 | 15 min | 11.01 | Include link |
| ☐ | 11.05 | Add website to Twitter | Link in profile | 🔴 | 5 min | 11.04 |  |
| ☐ | 11.06 | Create Instagram account | @turbomindz or similar | 🟡 | 15 min | None |  |
| ☐ | 11.07 | Set Instagram profile picture | Upload logo | 🟡 | 5 min | 11.06 |  |
| ☐ | 11.08 | Write Instagram bio | Compelling bio with CTA | 🟡 | 15 min | 11.06 | Link in bio |
| ☐ | 11.09 | Set up Linktree/bio link | Multiple links for IG | 🟡 | 15 min | 11.08 |  |
| ☐ | 11.10 | Write social post 1 | Project reveal/announcement | 🔴 | 20 min | 11.05 | Launch hook |
| ☐ | 11.11 | Create graphic for post 1 | Visual for announcement | 🔴 | 20 min | 11.10, Week 10 |  |
| ☐ | 11.12 | Write social post 2 | How It Works thread (8 parts) | 🔴 | 45 min | 11.10 | Educational |
| ☐ | 11.13 | Write social post 3 | Marketplace explainer | 🔴 | 20 min | 11.12 | Categories + tags |
| ☐ | 11.14 | Create graphic for post 3 | Marketplace visual | 🔴 | 20 min | 11.13 |  |
| ☐ | 11.15 | Write social post 4 | Theme rooms explainer | 🔴 | 20 min | 11.13 | Topics-based |
| ☐ | 11.16 | Create graphic for post 4 | Themes visual | 🔴 | 20 min | 11.15 |  |
| ☐ | 11.17 | Write social post 5 | Marriage concept | 🔴 | 20 min | 11.15 | Core mechanic |
| ☐ | 11.18 | Write social post 6 | Tag system explainer | 🟡 | 15 min | 11.17 |  |
| ☐ | 11.19 | Write social post 7 | Philosophy quote post | 🟡 | 15 min | 11.17 | From collection |
| ☐ | 11.20 | Create graphic for post 7 | Quote card | 🟡 | 15 min | 11.19, 10.26 |  |
| ☐ | 11.21 | Write social post 8 | Team/mission intro | 🟡 | 15 min | 11.19 |  |
| ☐ | 11.22 | Write social post 9 | Community preview | 🟡 | 15 min | 11.21 | Discord teaser |
| ☐ | 11.23 | Write social post 10 | Coming soon/countdown | 🟡 | 15 min | 11.22 | Build anticipation |
| ☐ | 11.24 | Post project reveal (Twitter) | First major public post | 🔴 | 10 min | 11.10, 11.11 | Pin it |
| ☐ | 11.25 | Post How It Works thread | Educational content | 🔴 | 15 min | 11.12 | Day after reveal |
| ☐ | 11.26 | Set up Buffer/Later | Social scheduling tool | 🟡 | 20 min | None | Free tier |
| ☐ | 11.27 | Schedule posts for 2 weeks | Queue remaining content | 🔴 | 30 min | 11.26, 11.13-11.23 | Consistent presence |
| ☐ | 11.28 | List 20 target influencers | Art, philosophy, NFT accounts | 🟡 | 1 hr | None | Relevant audience |
| ☐ | 11.29 | Research influencer contacts | Find DM/email for each | 🟡 | 45 min | 11.28 |  |
| ☐ | 11.30 | Draft influencer outreach | Template message | 🟡 | 20 min | 11.29 | Personalize later |
| ☐ | 11.31 | Send outreach batch 1 | Contact first 5 influencers | 🟡 | 45 min | 11.30 | Personalize each |
| ☐ | 11.32 | Create Mailchimp account | Sign up (free tier) | 🟡 | 15 min | None |  |
| ☐ | 11.33 | Create email list | “Turbomindz Updates” | 🟡 | 10 min | 11.32 |  |
| ☐ | 11.34 | Design email signup form | Branded form | 🟡 | 20 min | 11.33 |  |
| ☐ | 11.35 | Embed form on website | Add to Carrd site | 🟡 | 15 min | 11.34, Week 9 |  |
| ☐ | 11.36 | Write welcome email | Auto-email for new signups | 🟡 | 30 min | 11.33 | Warm intro |
| ☐ | 11.37 | Order Empty Frame packages | Purchase 100 frames | 🟡 | 30 min | None | Physical promo |
| ☐ | 11.38 | Create QR codes | Links to website | 🟡 | 20 min | Week 9 site |  |
| ☐ | 11.39 | Write handwritten note template | For frame packages | 🟡 | 15 min | None | Personal touch |
| ☐ | 11.40 | Print frame insert materials | QR codes, notes | 🟡 | 30 min | 11.38, 11.39 |  |

Week 11 Subtotal: 40 tasks, ~12.5 hours

## Week 12: Community Building

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 12.01 | Create public Discord invite | Permanent invite link | 🔴 | 10 min | Week 5 Discord | Non-expiring |
| ☐ | 12.02 | Open Discord to public | Remove any restrictions | 🔴 | 5 min | 12.01 | Go time |
| ☐ | 12.03 | Announce Discord on Twitter | Post with invite link | 🔴 | 15 min | 12.01, Week 11 |  |
| ☐ | 12.04 | Announce Discord on Instagram | Stories + feed post | 🟡 | 15 min | 12.01 |  |
| ☐ | 12.05 | Create whitelist signup | Premint.xyz or Google Form | 🟡 | 30 min | None | Early access |
| ☐ | 12.06 | Announce whitelist | Share signup link | 🟡 | 10 min | 12.05 |  |
| ☐ | 12.07 | Schedule Twitter Space | “Introducing Turbomindz” | 🟡 | 15 min | Week 11 Twitter |  |
| ☐ | 12.08 | Announce Twitter Space | Promote upcoming Space | 🟡 | 10 min | 12.07 |  |
| ☐ | 12.09 | Host Twitter Space | 30-45 min live session | 🟡 | 1 hr | 12.08 | Intro + Q&A |
| ☐ | 12.10 | Twitter engagement (Day 1) | Respond, retweet, engage | 🔴 | 1 hr | Week 11 |  |
| ☐ | 12.11 | Twitter engagement (Day 2) | Daily engagement | 🔴 | 1 hr | 12.10 |  |
| ☐ | 12.12 | Twitter engagement (Day 3) | Daily engagement | 🔴 | 1 hr | 12.11 |  |
| ☐ | 12.13 | Twitter engagement (Day 4) | Daily engagement | 🔴 | 1 hr | 12.12 |  |
| ☐ | 12.14 | Twitter engagement (Day 5) | Daily engagement | 🔴 | 1 hr | 12.13 |  |
| ☐ | 12.15 | Twitter engagement (Day 6) | Daily engagement | 🔴 | 1 hr | 12.14 |  |
| ☐ | 12.16 | Twitter engagement (Day 7) | Daily engagement | 🔴 | 1 hr | 12.15 |  |
| ☐ | 12.17 | Discord engagement (daily) | Welcome, answer, facilitate | 🔴 | 30 min/day | 12.02 | Build culture |
| ☐ | 12.18 | Send influencer batch 2 | Contact next 5 influencers | 🟡 | 45 min | Week 11.31 |  |
| ☐ | 12.19 | Follow up with batch 1 | Check on first outreach | 🟡 | 20 min | Week 11.31 |  |
| ☐ | 12.20 | Assemble Empty Frame packages | Prepare 50 packages | 🟡 | 2 hrs | Week 11.37-40 |  |
| ☐ | 12.21 | Create shipping list (Wave 1) | 25 influencer addresses | 🟡 | 30 min | 12.20 |  |
| ☐ | 12.22 | Ship Empty Frames (Wave 1) | Send first 25 packages | 🟡 | 1.5 hrs | 12.21 | Post office |
| ☐ | 12.23 | Write press release | Full launch announcement | 🟡 | 1.5 hrs | None | Professional |
| ☐ | 12.24 | Review press release | Proofread, fact-check | 🟡 | 20 min | 12.23 |  |
| ☐ | 12.25 | Finalize press kit | Add press release | 🟡 | 15 min | 12.24, Week 10.40 |  |
| ☐ | 12.26 | List press contacts | NFT/art media outlets | 🟡 | 45 min | None | 15-20 contacts |
| ☐ | 12.27 | Send first newsletter | Update to early signups | 🟡 | 30 min | Week 11 Mailchimp |  |
| ☐ | 12.28 | Track community metrics | Document growth | 🟡 | 20 min | None | Spreadsheet |
| ☐ | 12.29 | Create mock sale listing | Demonstrate in Discord | 🔴 | 30 min | Week 8 | With tags |
| ☐ | 12.30 | Demonstrate tag usage | Show proper formatting | 🔴 | 20 min | 12.29 | Educate members |
| ☐ | 12.31 | Run mock trade publicly | Show full process | 🔴 | 1 hr | 12.30 | Proof of concept |
| ☐ | 12.32 | Document demonstration | Screenshots/recording | 🟡 | 20 min | 12.31 | For content |
| ☐ | 12.33 | Pre-launch team meeting | Verify all systems ready | 🔴 | 1 hr | All above | Go/no-go |
| ☐ | 12.34 | Update project tracker | Record Week 12 progress | 🟡 | 15 min | All above |  |

Week 12 Subtotal: 34 tasks, ~22 hours

# PHASE 3: LAUNCH (Weeks 13-16)

## Week 13: Final Preparations

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 13.01 | Final QA: Images 1-25 | Review each for quality | 🔴 | 45 min | Week 4 | One by one |
| ☐ | 13.02 | Final QA: Images 26-50 | Review each for quality | 🔴 | 45 min | 13.01 |  |
| ☐ | 13.03 | Final QA: Metadata 1-25 | Verify JSON correctness | 🔴 | 30 min | Week 4 |  |
| ☐ | 13.04 | Final QA: Metadata 26-50 | Verify JSON correctness | 🔴 | 30 min | 13.03 |  |
| ☐ | 13.05 | Verify OpenSea settings | Check royalties, links, description | 🔴 | 15 min | Week 5 |  |
| ☐ | 13.06 | Test Guild.xyz (final) | Verify gating still works | 🔴 | 15 min | Week 6 |  |
| ☐ | 13.07 | Test Snapshot (final) | Verify voting works | 🟡 | 10 min | Week 6 |  |
| ☐ | 13.08 | Schedule launch team meeting | Set date/time for briefing | 🔴 | 10 min | None |  |
| ☐ | 13.09 | Create launch day schedule | Minute-by-minute plan | 🔴 | 30 min | 13.08 |  |
| ☐ | 13.10 | Create launch day checklist | Detailed task list | 🔴 | 20 min | 13.09 |  |
| ☐ | 13.11 | Hold launch briefing | Team call | 🔴 | 1 hr | 13.08-13.10 | Everyone aligned |
| ☐ | 13.12 | Write launch announcement | Twitter/Discord announcement | 🔴 | 30 min | None |  |
| ☐ | 13.13 | Create launch graphics | Visuals for announcement | 🔴 | 30 min | 13.12 |  |
| ☐ | 13.14 | Write progress update 1 | Midday update template | 🔴 | 15 min | None |  |
| ☐ | 13.15 | Write progress update 2 | Afternoon update template | 🔴 | 15 min | 13.14 |  |
| ☐ | 13.16 | Write day recap | End-of-day template | 🔴 | 15 min | 13.15 |  |
| ☐ | 13.17 | Schedule launch content | Pre-schedule what possible | 🔴 | 20 min | 13.12-13.16 |  |
| ☐ | 13.18 | Draft whitelist email | Launch announcement for list | 🔴 | 20 min | None |  |
| ☐ | 13.19 | Schedule whitelist email | Timed for launch | 🔴 | 10 min | 13.18 |  |
| ☐ | 13.20 | Create countdown posts | Daily teasers (Day -3, -2, -1) | 🔴 | 30 min | None | Build excitement |
| ☐ | 13.21 | Post countdown Day -3 | First countdown | 🔴 | 10 min | 13.20 |  |
| ☐ | 13.22 | Post countdown Day -2 | Second countdown | 🔴 | 10 min | 13.21 |  |
| ☐ | 13.23 | Post countdown Day -1 | Final countdown | 🔴 | 10 min | 13.22 |  |
| ☐ | 13.24 | Final website review | Check all content, links | 🔴 | 20 min | Week 9-10 |  |
| ☐ | 13.25 | Update website for launch | Any last-minute changes | 🟡 | 15 min | 13.24 |  |
| ☐ | 13.26 | Confirm team availability | Everyone confirmed for launch | 🔴 | 10 min | All team |  |
| ☐ | 13.27 | Prepare emergency contacts | Phone/Discord for all team | 🟡 | 10 min | 13.26 |  |
| ☐ | 13.28 | Create shipping list (Wave 2) | Remaining 25 frame addresses | 🟡 | 20 min | Week 12.20 |  |
| ☐ | 13.29 | Ship Empty Frames (Wave 2) | Send remaining 25 packages | 🟡 | 1.5 hrs | 13.28 |  |
| ☐ | 13.30 | Get good night’s sleep | Rest before launch | 🔴 | 8 hrs | All above | Seriously |

Week 13 Subtotal: 30 tasks, ~12 hours (excluding sleep)

## Week 14: MINT LAUNCH 🚀

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 14.01 | Wake up early | Prepare for launch | 🔴 | - | Week 13 |  |
| ☐ | 14.02 | Team check-in call | Morning sync (08:00 UTC) | 🔴 | 30 min | All team | Final go/no-go |
| ☐ | 14.03 | Review launch checklist | Verify everything ready | 🔴 | 15 min | 14.02 |  |
| ☐ | 14.04 | Go to OpenSea | Navigate to collection | 🔴 | 5 min | 14.03 |  |
| ☐ | 14.05 | Mint NFT #1-10 | Create first batch | 🔴 | 15 min | 14.04, Week 4 |  |
| ☐ | 14.06 | Mint NFT #11-20 | Create second batch | 🔴 | 15 min | 14.05 |  |
| ☐ | 14.07 | Mint NFT #21-30 | Create third batch | 🔴 | 15 min | 14.06 |  |
| ☐ | 14.08 | Mint NFT #31-40 | Create fourth batch | 🔴 | 15 min | 14.07 |  |
| ☐ | 14.09 | Mint NFT #41-50 | Create final batch | 🔴 | 15 min | 14.08 |  |
| ☐ | 14.10 | Verify all 50 NFTs display | Check each one | 🔴 | 30 min | 14.09 |  |
| ☐ | 14.11 | Set prices on NFTs | List at determined prices | 🔴 | 20 min | 14.10 |  |
| ☐ | 14.12 | Make collection public | Unhide if hidden | 🔴 | 5 min | 14.11 |  |
| ☐ | 14.13 | Post Discord announcement | “We’re LIVE!” | 🔴 | 10 min | 14.12 | ~10:00 UTC |
| ☐ | 14.14 | Post Twitter announcement | Launch tweet + pin | 🔴 | 10 min | 14.13 |  |
| ☐ | 14.15 | Post Instagram announcement | Feed + stories | 🟡 | 10 min | 14.14 |  |
| ☐ | 14.16 | Send whitelist email | Notify early signups | 🔴 | 5 min | 14.14 | Pre-scheduled |
| ☐ | 14.17 | Send press release | Email to media list | 🟡 | 20 min | 14.14 |  |
| ☐ | 14.18 | Discord support (10:30-12:00) | Answer questions, help buyers | 🔴 | 1.5 hrs | 14.13 |  |
| ☐ | 14.19 | Twitter engagement (10:30-12:00) | Respond, retweet, celebrate | 🔴 | 1.5 hrs | 14.14 |  |
| ☐ | 14.20 | Post progress update 1 (12:00) | Midday stats | 🔴 | 15 min | 14.18 |  |
| ☐ | 14.21 | Lunch break | Rotate coverage | 🔴 | 30 min | 14.20 |  |
| ☐ | 14.22 | Discord support (13:00-15:00) | Continue support | 🔴 | 2 hrs | 14.21 |  |
| ☐ | 14.23 | Twitter engagement (13:00-15:00) | Continue engagement | 🔴 | 2 hrs | 14.21 |  |
| ☐ | 14.24 | Post progress update 2 (15:00) | Afternoon stats | 🔴 | 15 min | 14.23 |  |
| ☐ | 14.25 | Respond to press inquiries | Answer any media questions | 🟡 | 30 min | 14.17 |  |
| ☐ | 14.26 | Discord support (15:00-17:00) | Continue support | 🔴 | 2 hrs | 14.24 |  |
| ☐ | 14.27 | Twitter engagement (15:00-17:00) | Continue engagement | 🔴 | 2 hrs | 14.24 |  |
| ☐ | 14.28 | Monitor for technical issues | Watch for problems | 🔴 | Ongoing | All above |  |
| ☐ | 14.29 | Document first sales | Screenshots, stats | 🟡 | 30 min | 14.11+ | For content |
| ☐ | 14.30 | Post end-of-day recap (18:00) | Day 1 summary | 🔴 | 20 min | All above |  |
| ☐ | 14.31 | Team debrief call (20:00) | Review day | 🔴 | 45 min | 14.30 |  |
| ☐ | 14.32 | Document any issues | Record problems for fixing | 🟡 | 20 min | 14.31 |  |
| ☐ | 14.33 | Plan Day 2 adjustments | Based on learnings | 🔴 | 30 min | 14.32 |  |
| ☐ | 14.34 | Day 2: Morning support | Continue engagement | 🔴 | 2 hrs | 14.33 |  |
| ☐ | 14.35 | Day 2: Afternoon support | Continue engagement | 🔴 | 2 hrs | 14.34 |  |
| ☐ | 14.36 | Day 2: Daily recap | Post update | 🟡 | 15 min | 14.35 |  |
| ☐ | 14.37 | Day 3-7: Daily support | Continued presence | 🔴 | 2 hrs/day | 14.36 |  |
| ☐ | 14.38 | Day 3-7: Daily recaps | Post updates | 🟡 | 15 min/day | 14.37 |  |

Week 14 Subtotal: 38 tasks, ~25+ hours (intensive)

## Week 15: Post-Launch Activation (Part 1)

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 15.01 | Announce Registry opening | “#marriage-requests is OPEN” | 🔴 | 10 min | Week 14 |  |
| ☐ | 15.02 | Post Registry instructions | Detailed how-to guide | 🔴 | 20 min | 15.01 | Pin it |
| ☐ | 15.03 | Monitor first Marriage request | Watch for first submission | 🔴 | Ongoing | 15.02 |  |
| ☐ | 15.04 | Process Marriage request 1 | Scribe verification | 🔴 | 30 min | 15.03 | First real one |
| ☐ | 15.05 | Process Marriage request 2 | Continue processing | 🔴 | 30 min | 15.04 |  |
| ☐ | 15.06 | Process Marriage request 3 | Continue processing | 🔴 | 30 min | 15.05 |  |
| ☐ | 15.07 | Process Marriage requests 4-5 | If received | 🔴 | 1 hr | 15.06 |  |
| ☐ | 15.08 | Create example seller listing | Model post with correct tags | 🔴 | 30 min | Week 8 | Template |
| ☐ | 15.09 | Post example in #paintings | Demonstrate in first category | 🔴 | 15 min | 15.08 |  |
| ☐ | 15.10 | Post examples in other categories | Demonstrate tag usage | 🟡 | 45 min | 15.09 | 2-3 more |
| ☐ | 15.11 | Announce marketplace is live | Official trading announcement | 🔴 | 10 min | 15.10 |  |
| ☐ | 15.12 | Monitor first negotiation | Watch for first offer | 🔴 | Ongoing | 15.11 |  |
| ☐ | 15.13 | Guide first negotiation | Help if needed | 🔴 | 30 min | 15.12 | Don’t interfere |
| ☐ | 15.14 | Monitor first sale agreement | Watch for confirmation | 🔴 | Ongoing | 15.13 |  |
| ☐ | 15.15 | Guide first OpenSea execution | Help with private sale | 🔴 | 20 min | 15.14 |  |
| ☐ | 15.16 | Monitor first shipping | Watch for tracking | 🔴 | Ongoing | 15.15 |  |
| ☐ | 15.17 | Monitor first delivery | Watch for confirmation | 🔴 | Ongoing | 15.16 |  |
| ☐ | 15.18 | Document first trade | Full case study | 🟡 | 1.5 hrs | 15.17 | Content gold |
| ☐ | 15.19 | Post first trade celebration | Announce milestone | 🟡 | 15 min | 15.18 |  |
| ☐ | 15.20 | Launch Philosophy Challenge 1 | “Classical Foundations” theme | 🟡 | 45 min | Week 14+ |  |
| ☐ | 15.21 | Start Witnessed Deal series | First episode/thread | 🟡 | 1 hr | 15.18 | Ongoing series |
| ☐ | 15.22 | Ask for testimonials | Reach out to first buyers | 🟡 | 30 min | Week 14+ |  |
| ☐ | 15.23 | Collect testimonials | Gather 3+ quotes | 🟡 | 30 min | 15.22 |  |
| ☐ | 15.24 | Seed theme room discussions | Start conversations in each | 🟡 | 45 min | Week 14+ |  |
| ☐ | 15.25 | Daily Twitter engagement | Continue presence | 🔴 | 1 hr/day | Week 14 |  |
| ☐ | 15.26 | Daily Discord management | Continue presence | 🔴 | 1 hr/day | Week 14 |  |
| ☐ | 15.27 | Address any issues | Fix problems found | 🔴 | Varies | Ongoing |  |

Week 15 Subtotal: 27 tasks, ~15+ hours

## Week 16: Post-Launch Activation (Part 2)

| ☐ | ID | Task | Description | Priority | Est. Time | Dependencies | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | 16.01 | Gather Week 1-2 stats | Compile all metrics | 🔴 | 1 hr | Week 14-15 |  |
| ☐ | 16.02 | Write transparency report | Full public report | 🔴 | 2 hrs | 16.01 | Honest |
| ☐ | 16.03 | Design transparency report | Formatted for sharing | 🟡 | 30 min | 16.02 |  |
| ☐ | 16.04 | Publish transparency report | Post to Discord + website | 🔴 | 15 min | 16.03 |  |
| ☐ | 16.05 | Create Trust Scoreboard | Real-time metrics display | 🟡 | 1.5 hrs | 16.01 | Notion embed |
| ☐ | 16.06 | Add Trust Scoreboard to website | Embed on site | 🟡 | 20 min | 16.05 |  |
| ☐ | 16.07 | Create Provenance Museum | Notion database for trades | 🟡 | 1.5 hrs | Week 15 trades |  |
| ☐ | 16.08 | Add Provenance Museum to website | Embed on site | 🟡 | 20 min | 16.07 |  |
| ☐ | 16.09 | Write post-launch newsletter | Email update | 🟡 | 45 min | 16.02 |  |
| ☐ | 16.10 | Send post-launch newsletter | Email to subscribers | 🟡 | 10 min | 16.09 |  |
| ☐ | 16.11 | Schedule post-launch Twitter Space | AMA about first 2 weeks | 🟡 | 15 min | None |  |
| ☐ | 16.12 | Announce Twitter Space | Promote event | 🟡 | 10 min | 16.11 |  |
| ☐ | 16.13 | Host post-launch Twitter Space | Live AMA | 🟡 | 1 hr | 16.12 |  |
| ☐ | 16.14 | Analyze launch metrics | Full analysis document | 🔴 | 1.5 hrs | 16.01 |  |
| ☐ | 16.15 | Identify what worked | List successes | 🔴 | 30 min | 16.14 |  |
| ☐ | 16.16 | Identify what didn’t work | List improvements | 🔴 | 30 min | 16.14 |  |
| ☐ | 16.17 | Create Phase 4 plan | Update strategy | 🔴 | 1.5 hrs | 16.15-16.16 |  |
| ☐ | 16.18 | Post thank you (Twitter) | Thank early supporters | 🟡 | 15 min | None |  |
| ☐ | 16.19 | Post thank you (Discord) | Thank community | 🟡 | 15 min | None |  |
| ☐ | 16.20 | Assess second drop demand | Should we create more? | 🟡 | 30 min | 16.14 |  |
| ☐ | 16.21 | Begin second drop planning | If demand exists | 🟡 | 1 hr | 16.20 |  |
| ☐ | 16.22 | Review Scribe performance | Provide feedback | 🟡 | 30 min | Week 15 |  |
| ☐ | 16.23 | Phase 3 completion meeting | Team review | 🔴 | 1 hr | All above |  |
| ☐ | 16.24 | Update SOPs | Based on learnings | 🟡 | 1 hr | 16.16 |  |
| ☐ | 16.25 | Update FAQ | Add new common questions | 🟡 | 30 min | Week 15 |  |
| ☐ | 16.26 | Continue daily engagement | Maintain presence | 🔴 | 2 hrs/day | Ongoing |  |

Week 16 Subtotal: 26 tasks, ~19 hours

# PHASE 4: OPERATIONS & GROWTH (Weeks 17-32)

## Ongoing Weekly Tasks (Repeat Each Week)

| ☐ | ID | Task | Description | Priority | Est. Time | Frequency |
| --- | --- | --- | --- | --- | --- | --- |
| ☐ | W.01 | Process Marriage requests | Verify submissions within 48h | 🔴 | 30 min/day | Daily |
| ☐ | W.02 | Moderate marketplace | Watch for violations, manage tags | 🔴 | 30 min/day | Daily |
| ☐ | W.03 | Social media engagement | Post, respond, engage | 🔴 | 1 hr/day | Daily |
| ☐ | W.04 | Discord community management | Welcome, answer, facilitate | 🔴 | 30 min/day | Daily |
| ☐ | W.05 | Check for disputes | Monitor #tribunal-cases | 🔴 | 15 min/day | Daily |
| ☐ | W.06 | Update analytics | Record weekly metrics | 🟡 | 30 min | Weekly |
| ☐ | W.07 | Team sync meeting | Check-in with Scribes | 🟡 | 30 min | Weekly |
| ☐ | W.08 | Create weekly content | New posts, graphics | 🟡 | 2 hrs | Weekly |
| ☐ | W.09 | Philosophy Challenge | New weekly prompt | 🟡 | 1 hr | Weekly |
| ☐ | W.10 | Newsletter | Bi-weekly email | 🟡 | 1 hr | Bi-weekly |
| ☐ | W.11 | Transparency report | Monthly public update | 🔴 | 2 hrs | Monthly |
| ☐ | W.12 | Provenance Help Desk | Answer authentication Qs | 🟡 | As needed | As needed |

Weekly Ongoing Total: ~15-20 hours/week

## Month 5 Milestones (Weeks 17-20)

| ☐ | ID | Task | Description | Priority | Target Week |
| --- | --- | --- | --- | --- | --- |
| ☐ | M5.01 | Announce Elder elections | Explain process, timeline | 🔴 | 17 |
| ☐ | M5.02 | Open Elder nominations | Collect candidate names | 🔴 | 17 |
| ☐ | M5.03 | Verify Elder eligibility | 3+ months, 1+ trade | 🔴 | 17-18 |
| ☐ | M5.04 | Create Snapshot election | Set up voting | 🔴 | 18 |
| ☐ | M5.05 | Run 7-day voting period | Community votes | 🔴 | 18-19 |
| ☐ | M5.06 | Announce elected Elders | 5 Elders selected | 🔴 | 19 |
| ☐ | M5.07 | Train new Elders | Tribunal process | 🔴 | 19 |
| ☐ | M5.08 | Launch Guild Partnership #1 | Paintings/drawings community | 🟡 | 17 |
| ☐ | M5.09 | Launch Guild Partnership #2 | Photography community | 🟡 | 19 |
| ☐ | M5.10 | Start Member Origin Stories | First 3 interviews | 🟡 | 17-20 |
| ☐ | M5.11 | Begin Analog Bridge outreach | Contact 5 galleries | 🟡 | 18 |
| ☐ | M5.12 | Secure first gallery partner | At least 1 confirmed | 🟡 | 20 |
| ☐ | M5.13 | Reach 25+ completed trades | Milestone | 🔴 | 20 |
| ☐ | M5.14 | Reach 40+ Marriages | Milestone | 🔴 | 20 |
| ☐ | M5.15 | First community governance vote | Non-Elder proposal | 🟡 | 19-20 |

## Month 6 Milestones (Weeks 21-24)

| ☐ | ID | Task | Description | Priority | Target Week |
| --- | --- | --- | --- | --- | --- |
| ☐ | M6.01 | Launch Guild Partnership #3 | Digital/generative community | 🟡 | 21 |
| ☐ | M6.02 | Launch Guild Partnership #4 | Prints community | 🟡 | 23 |
| ☐ | M6.03 | Assess second drop viability | Review demand data | 🟡 | 21 |
| ☐ | M6.04 | Generate second drop art | If proceeding (25-50 pieces) | 🟡 | 21-22 |
| ☐ | M6.05 | Launch second drop | If proceeding | 🟡 | 24 |
| ☐ | M6.06 | Reach 50+ completed trades | Milestone | 🔴 | 24 |
| ☐ | M6.07 | Reach 75+ Marriages | Milestone | 🔴 | 24 |
| ☐ | M6.08 | Compile 6-month stats | Comprehensive data | 🔴 | 24 |
| ☐ | M6.09 | Write 6-month report | Public transparency report | 🔴 | 24 |
| ☐ | M6.10 | Publish 6-month report | Discord + website + social | 🔴 | 24 |
| ☐ | M6.11 | Assess operations sustainability | Are fees covering costs? | 🔴 | 24 |
| ☐ | M6.12 | 10+ Trusted Sellers | Badge milestone | 🟡 | 24 |
| ☐ | M6.13 | Community-proposed Charter change | Passes via vote | 🟡 | 23-24 |
| ☐ | M6.14 | Second gallery partnership | Analog Bridge expansion | 🟡 | 24 |

## Months 7-8 (Weeks 25-32)

| ☐ | ID | Task | Description | Priority | Target Week |
| --- | --- | --- | --- | --- | --- |
| ☐ | M7.01 | Write case study | Detailed project analysis | 🟡 | 26 |
| ☐ | M7.02 | Publish case study | Blog/Medium/website | 🟡 | 26 |
| ☐ | M7.03 | Secure podcast appearance #1 | Speaking opportunity | 🟡 | 25-28 |
| ☐ | M7.04 | Secure podcast appearance #2 | Speaking opportunity | 🟡 | 25-28 |
| ☐ | M7.05 | Secure podcast appearance #3 | Speaking opportunity | 🟡 | 25-32 |
| ☐ | M7.06 | Pitch to major publication | NFT/art media | 🟡 | 27 |
| ☐ | M7.07 | Secure media feature | Major coverage | 🟡 | 28-32 |
| ☐ | M7.08 | Design ambassador program | Structure, benefits, requirements | 🟡 | 27 |
| ☐ | M7.09 | Launch ambassador program | Recruit advocates | 🟡 | 28 |
| ☐ | M7.10 | Guild Partnership #5 | Fifth category partnership | 🟡 | 28 |
| ☐ | M7.11 | Gallery partnership #3 | Third physical location | 🟡 | 30 |
| ☐ | M7.12 | Reach 100+ completed trades | Major milestone | 🔴 | 32 |
| ☐ | M7.13 | Reach 100+ Marriages | Major milestone | 🔴 | 32 |
| ☐ | M7.14 | 25+ Trusted Sellers | Ecosystem maturity | 🟡 | 32 |
| ☐ | M7.15 | Year 1 planning session | Strategic planning | 🔴 | 32 |

# 📊 SUMMARY STATISTICS

## Total Task Count by Phase

| Phase | Weeks | Tasks | Est. Hours |
| --- | --- | --- | --- |
| Phase 1: Foundation | 1-8 | 199 | ~90 |
| Phase 2: Pre-Launch | 9-12 | 150 | ~57 |
| Phase 3: Launch | 13-16 | 121 | ~71 |
| Phase 4: Operations | 17-32 | 44 milestones + ongoing | ~280 |
| TOTAL | 32 weeks | 514+ tasks | ~498+ hours |

## Tasks by Week

| Week | Phase | Task Count |
| --- | --- | --- |
| 1 | Foundation | 17 |
| 2 | Foundation | 17 |
| 3 | Foundation | 15 |
| 4 | Foundation | 16 |
| 5 | Foundation | 50 |
| 6 | Foundation | 31 |
| 7 | Foundation | 23 |
| 8 | Foundation | 30 |
| 9 | Pre-Launch | 36 |
| 10 | Pre-Launch | 40 |
| 11 | Pre-Launch | 40 |
| 12 | Pre-Launch | 34 |
| 13 | Launch | 30 |
| 14 | Launch | 38 |
| 15 | Launch | 27 |
| 16 | Launch | 26 |
| 17-20 | Operations | 15 milestones |
| 21-24 | Operations | 14 milestones |
| 25-32 | Operations | 15 milestones |

## Priority Distribution

| Priority | Count | Percentage |
| --- | --- | --- |
| 🔴 Critical | ~280 | ~55% |
| 🟡 Important | ~200 | ~39% |
| 🟢 Nice to Have | ~34 | ~6% |

# ✅ HOW TO USE THIS CHECKLIST

## For Google Sheets

- Copy all tables

- Paste into Google Sheets

- Replace ☐ column with actual checkboxes (Insert > Checkbox)

- Add conditional formatting for priorities

- Filter by Status, Week, or Priority

## For Notion

- Create new database

- Properties: Status, Week, Priority, Time, Dependencies

- Import tasks

- Create views: By Week, By Priority, Incomplete Only

## For Project Management Tools

Asana/Monday.com/ClickUp: 1. Create project 2. Create sections for each Phase 3. Import tasks 4. Set due dates based on Week 5. Assign owners 6. Add dependencies

# 🎯 CRITICAL PATH REMINDER

These tasks MUST be completed on schedule:

Week 1: Quote research ─────────────────┐
Week 3-4: Generate 50 artworks ─────────┤
Week 4: IPFS upload ────────────────────┤
Week 5: OpenSea + Discord setup ────────┤
Week 6: Guild.xyz token gating ─────────┤
Week 7: Finalize Charter ───────────────┤
Week 8: Train Scribes, test workflows ──┤
Week 9: Build website ──────────────────┤
Week 12: Build 200+ community ──────────┤
Week 13: Final QA, team brief ──────────┤
Week 14: ★ MINT LAUNCH ★ ───────────────┘

Document Complete: 514+ tasks across 32 weeks

Good luck with Turbomindz! Create. Connect. Trade Fair. 🎨