# Please produce a detailed task list with a timeline of production, add specific instructions on each task.

# Please produce a detailed task list with a timeline of production, add specific instructions on each task.

# 📋 TURBOMINDZ NFT PRODUCTION WORKFLOW

## Complete Task List with Timeline & Specific Instructions

# 🗓️ MASTER TIMELINE OVERVIEW

══════════════════════════════════════════════════════════════════════════════════
                        32-WEEK PRODUCTION TIMELINE
══════════════════════════════════════════════════════════════════════════════════

WEEK:  1  2  3  4  5  6  7  8  9  10 11 12 13 14 15 16 17-20 21-24 25-28 29-32
       ├────────────────────────┤├────────────────────┤├─────────────────────────┤
              PHASE 1                   PHASE 2              PHASE 3 & 4
            FOUNDATION               PRE-LAUNCH &          OPERATIONS &
           (Weeks 1-8)              LAUNCH (9-16)         GROWTH (17-32)

NFT Production: 448 total over 32 weeks = 14 NFTs/week = 2 NFTs/day
Quote Research: Complete by Week 8, ongoing curation thereafter
Art Generation: Begins Week 3, continuous through Week 32

══════════════════════════════════════════════════════════════════════════════════

# PHASE 1: FOUNDATION (Weeks 1-8)

## Building the Infrastructure

## 📅 WEEK 1: PLANNING & LEGAL FOUNDATION

Objective: Establish project foundation, secure assets, compile research [2]

### Task 1.1: Project Name & Domain Registration

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | None |

Specific Instructions: 1. Confirm “Turbomindz” as final project name 2. Check domain availability at Namecheap/GoDaddy 3. Register: turbomindz.xyz, turbomindz.com, turbomindz.io 4. Set up auto-renewal for all domains 5. Configure DNS to point to placeholder page

Deliverable: Domain registration confirmations saved to project folder

### Task 1.2: Treasury Wallet Creation

| Field | Details |
| --- | --- |
| Duration | 1 hour |
| Priority | 🔴 Critical |
| Dependencies | None |

Specific Instructions: 1. Download MetaMask browser extension 2. Click “Create New Wallet” 3. Set strong password (16+ characters) 4. ⚠️ CRITICAL: Write 12-word seed phrase on PAPER - Never store digitally - Never screenshot - Store in secure physical location 5. Add Polygon Network: - Network Name: Polygon Mainnet - RPC URL: https://polygon-rpc.com - Chain ID: 137 - Currency: MATIC - Explorer: https://polygonscan.com 6. Fund with $50-100 MATIC for initial operations

Deliverable: Wallet address documented, seed phrase secured offline

### Task 1.3: Quote Research & Compilation (100+ Quotes)

| Field | Details |
| --- | --- |
| Duration | 8 hours |
| Priority | 🔴 Critical |
| Dependencies | Theme structure defined |

Specific Instructions:

Step 1: Set Up Quote Database (Google Sheets)

COLUMNS:
A: TM-ID (TM-001 through TM-448)
B: Quote Text (exact wording)
C: Author (full name with dates)
D: Source (original work, year)
E: Theme (one of 9 themes)
F: Visual Potential (1-10 rating)
G: Public Domain Status (verified Y/N)
H: Verification Sources (3 URLs minimum)
I: Date Added
J: Status (Pending/Approved/Used)

Step 2: Research by Theme [2] Allocate quotes per theme (approximately 50 per theme for 448 total):

| Theme | Color Code | Target Quotes | Research Sources |
| --- | --- | --- | --- |
| Classical Foundations | #1A237E | 50 | WikiQuote, Project Gutenberg, Stanford Encyclopedia |
| Enlightenment & Reason | #C9A227 | 50 | Enlightenment texts, philosophy databases |
| Existentialism & Modern | #4A148C | 50 | Existentialist works, 20th century philosophy |
| Mysticism & Esoterica | #00695C | 50 | Sacred texts, esoteric literature |
| Eastern Wisdom | #E65100 | 50 | Tao Te Ching, Buddhist texts, Vedic literature |
| Science, Media & Modernity | #607D8B | 50 | Scientific writings, media theory |
| Poetry, Aesthetics & Literature | #AD1457 | 50 | Poetry anthologies, literary criticism |
| Civic, Social & Moral | #B71C1C | 50 | Political philosophy, ethics texts |
| Psychology, Mind & Meaning | #00838F | 48 | Psychology texts, consciousness studies |

Step 3: Quote Evaluation Criteria For each quote, rate 1-10 on: - Profundity (1-10): Does it express deep insight? - Visual Potential (1-10): Can it be translated to imagery? - Universality (1-10): Does it resonate across cultures? - Only accept quotes scoring 7+ average

Step 4: Attribution Verification Checklist

□ Author death date confirmed (70+ years ago for public domain)
□ Original source work identified
□ Translation public domain verified (if applicable)
□ Cross-referenced 3+ scholarly sources
□ Wording matches original (not paraphrased)
□ No trademark issues

Deliverable: Database with 100+ verified quotes organized by theme

### Task 1.4: Legal Documentation Drafts

| Field | Details |
| --- | --- |
| Duration | 3 hours |
| Priority | 🟡 Important |
| Dependencies | Project scope defined |

Specific Instructions:

Terms of Service must include: 1. NFT ownership rights definition 2. Intellectual property clarifications 3. Marriage system legal framework 4. Trading rules and liability limitations 5. Dispute resolution process 6. Jurisdiction specification

Privacy Policy must include: 1. Data collection practices 2. Wallet address handling 3. Discord data usage 4. Cookie policy 5. GDPR compliance (if applicable) 6. Contact information

Template Resources: - Use Termly.io free generator as starting point - Review OpenSea’s terms for NFT-specific language - Consult similar phygital projects for marriage system precedent

Deliverable: Draft ToS and Privacy Policy documents

## 📅 WEEK 2: BRAND & IDENTITY DEVELOPMENT

Objective: Establish complete visual identity system [2] [4]

### Task 2.1: Color Palette Definition

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | None |

Specific Instructions:

Primary Palette:

TURBOMINDZ BRAND COLORS:

Primary:
├── Deep Teal: #1A3A3A (backgrounds, text)
├── Gold: #C9A227 (accents, highlights)
└── Cream: #F5F1E6 (backgrounds, contrast)

Secondary:
├── Orange: #FF6B35 (Cosmo's boots, CTAs)
├── Cyan: #00D4AA (Nova's skin)
└── Magenta: #AD1457 (accent highlights)

Theme Colors (for NFT organization):
├── Classical: #1A237E (Deep Blue)
├── Enlightenment: #C9A227 (Gold)
├── Existentialism: #4A148C (Purple)
├── Mysticism: #00695C (Emerald)
├── Eastern: #E65100 (Orange)
├── Science: #607D8B (Silver Blue)
├── Poetry: #AD1457 (Rose)
├── Civic: #B71C1C (Red)
└── Psychology: #00838F (Teal)

Deliverable: Color palette document with HEX, RGB, and CMYK values

### Task 2.2: Typography Selection

| Field | Details |
| --- | --- |
| Duration | 1 hour |
| Priority | 🟡 Important |
| Dependencies | None |

Specific Instructions:

Font Pairing:

HEADERS: Playfair Display (Google Fonts - Free)
- Weight: Bold (700)
- Use for: Titles, quotes, headlines
- Character: Classical, elegant, authoritative

BODY: Inter (Google Fonts - Free)
- Weight: Regular (400), Medium (500), Bold (700)
- Use for: Body text, UI elements, descriptions
- Character: Modern, clean, highly readable

ACCENT: Space Grotesk (Google Fonts - Free)
- Weight: Medium (500)
- Use for: NFT numbers, tags, technical info
- Character: Futuristic, tech-forward

Implementation: 1. Download fonts from Google Fonts 2. Install on local machine for design work 3. Add to website via Google Fonts CDN 4. Create font usage guide document

Deliverable: Typography guide with font files and usage rules

### Task 2.3: Logo Design

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Color palette, typography |

Specific Instructions:

Logo Requirements: 1. Works at small sizes (favicon 16x16px) 2. Recognizable as brain/canvas hybrid 3. Uses brand colors (teal, gold) 4. Works in single color (for stamps/watermarks) 5. Has horizontal and square variants

Design Specifications:

LOGO VARIANTS NEEDED:

1. Primary Logo (Horizontal)
   - Brain/canvas icon + "TURBOMINDZ" wordmark
   - Size: 200x50px minimum
   - Use on: Headers, documents, presentations

2. Icon Only (Square)
   - Brain/canvas symbol
   - Size: 50x50px minimum
   - Use on: Favicon, social profiles, avatar

3. Vertical Stack
   - Icon above wordmark
   - Size: 100x120px minimum
   - Use on: Social posts, merchandise

4. Monochrome Versions
   - White on dark
   - Dark on light
   - Single color gold

AI Prompt for Logo Concept:

Minimalist logo design combining a human brain silhouette 
with an artist's canvas frame, geometric style, clean lines, 
suitable for small sizes, uses deep teal and gold colors, 
modern and elegant, professional branding, vector art style 
--ar 1:1 --v 6

Deliverable: Logo files in SVG, PNG (transparent), and JPG formats

### Task 2.4: Visual Style Guide Creation

| Field | Details |
| --- | --- |
| Duration | 3 hours |
| Priority | 🟡 Important |
| Dependencies | Tasks 2.1-2.3 |

Specific Instructions:

Style Guide Contents:

TURBOMINDZ VISUAL STYLE GUIDE

SECTION 1: BRAND OVERVIEW
- Mission statement
- Brand voice (intelligent, accessible, warm)
- Key messages

SECTION 2: LOGO USAGE
- Clear space requirements
- Minimum sizes
- Incorrect usage examples
- Color variations

SECTION 3: COLOR PALETTE
- Primary colors with codes
- Secondary colors
- Theme-specific colors
- Color combinations do's and don'ts

SECTION 4: TYPOGRAPHY
- Font families
- Hierarchy rules
- Size scales
- Line spacing

SECTION 5: IMAGERY STYLE
- "Marble Renaissance Digital" aesthetic
- Classical + modern fusion
- Quality standards
- Photography guidelines

SECTION 6: APPLICATION EXAMPLES
- Social media templates
- Discord graphics
- Website sections
- Print materials

Deliverable: Complete brand style guide PDF (15-20 pages)

### Task 2.5: Character Design - Cosmo & Nova [4]

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🟡 Important |
| Dependencies | Visual style guide |

Specific Instructions:

Cosmo Character Sheet Requirements:

COSMO THE ASTRONAUT - FULL SPECIFICATIONS

PROPORTIONS:
- Pixar-cute chibi style (3 heads tall)
- Large head, chunky body
- Soft, squeezable appearance

COSTUME:
- White/cream spacesuit (#F5F1E6)
- SIGNATURE: Bright orange boots (#FF6B35)
- Orange accents: gloves, knee pads, backpack
- Teal trim details (#1A3A3A)

HELMET:
- Large spherical fishbowl
- Clear visor showing face
- Chrome neck ring
- Small bent antenna

FACE:
- Large round eyes with shiny pupils
- Small button nose
- Wide friendly smile
- Rosy cheeks (pink circles)
- Short brown hair

ACCESSORIES:
- Turbomindz logo badge on chest
- Orange backpack with art supplies
- Tethered floating golden NFT frame

Nova Character Sheet Requirements:

NOVA THE ALIEN - FULL SPECIFICATIONS

PROPORTIONS:
- 2/3 Cosmo's height
- Large smooth dome head
- Slim graceful body
- Always floating slightly

SKIN:
- Bright cyan/teal (#00D4AA)
- Gold bioluminescent patterns (#C9A227)
- Smooth glossy finish
- Subtle inner glow

EYES:
- HUGE almond-shaped (1/3 face width)
- Solid gold/amber (#FFB347)
- No visible pupils
- Inner glow effect

FEATURES:
- Three-fingered hands with gold tips
- Two small glowing antennae
- 3-4 floating light orbs around head
- Tiny gold infinity pendant

SPECIAL EFFECTS:
- Sparkle trail when moving
- Floating shadow below
- Gentle luminescence

Expression Sheets Needed: For both characters, create expression variations: 1. Happy/Excited 2. Curious/Wondering 3. Teaching/Explaining 4. Celebrating 5. Thinking/Contemplating

Deliverable: Character design sheets with front, side, 3/4 views and expressions

## 📅 WEEK 3: AI ART GENERATION (Part 1)

Objective: Generate first batch of 25 NFT artworks [1] [2]

### Task 3.1: Define Art Style Parameters

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Visual style guide |

Specific Instructions:

Master Art Style: “Marble Renaissance Digital”

CORE AESTHETIC ELEMENTS:

1. TEXTURE LAYERS:
   - Base: Smooth marble or aged parchment
   - Detail: Gold leaf, metallic accents
   - Atmosphere: Soft particles, divine light rays
   - Digital: Subtle modern polish

2. COMPOSITION RULES:
   - Center weight for philosophical gravity
   - Dramatic chiaroscuro lighting
   - Single focal figure/symbol
   - 2:3 aspect ratio (portrait orientation)

3. COLOR APPROACH:
   - Theme-specific dominant color
   - Gold accents universal
   - Rich, saturated tones
   - Museum-quality lighting

Theme-Specific Prompt Modifiers:

CLASSICAL FOUNDATIONS (#1A237E):
"deep blue background, classical Greek/Roman elements, 
marble textures, laurel wreaths, columns, balanced symmetry"

ENLIGHTENMENT (#C9A227):
"warm golden light, candles and books, rational symbols,
balanced scales, geometric precision, Age of Reason aesthetic"

EXISTENTIALISM (#4A148C):
"deep purple atmosphere, solitary figures, vast empty spaces,
dramatic shadows, modern abstraction elements"

MYSTICISM (#00695C):
"emerald mystical glow, sacred symbols, alchemical imagery,
hidden knowledge aesthetic, esoteric patterns"

EASTERN WISDOM (#E65100):
"burnt orange serenity, zen gardens, lotus flowers,
flowing water, minimalist elements, contemplative spaces"

SCIENCE/MEDIA (#607D8B):
"silver-blue tech aesthetic, cosmic elements, neurons,
scientific instruments, modern clean lines"

POETRY/AESTHETICS (#AD1457):
"rose romantic tones, flowers and nature, flowing fabrics,
artistic tools, beauty and emotion"

CIVIC/SOCIAL (#B71C1C):
"deep red passionate tones, justice symbols, community,
civic architecture, moral weight"

PSYCHOLOGY/MIND (#00838F):
"teal consciousness swirls, mind visualization, dreams,
psychological symbolism, inner exploration"

Deliverable: Complete art style specification document

### Task 3.2: Create Prompt Templates

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Art style parameters |

Specific Instructions:

Master Prompt Formula:

[CONCEPT BLOCK] + [STYLE BLOCK] + [COLOR BLOCK] + [TECHNICAL BLOCK] + [PARAMETERS]

Block Templates (Copy-Paste Ready):

CONCEPT BLOCK TEMPLATE:
"[Core philosophical concept from quote] visualized through 
[symbolic imagery], featuring [central visual element]"

STYLE BLOCK (Universal):
"classical Renaissance painting meets modern digital art, 
marble textures, gold leaf accents, museum-quality dramatic 
lighting, ethereal contemplative atmosphere, fine art 
gallery quality"

COLOR BLOCK TEMPLATE:
"deep [theme-color-name] background (#[HEX]), with warm gold 
accents, rich saturated tones, dramatic chiaroscuro"

TECHNICAL BLOCK:
"highly detailed, 8k resolution, professional art photography, 
sharp focus on central element, soft atmospheric depth"

PARAMETERS:
"--ar 2:3 --v 6 --s 250 --q 2"

Example Complete Prompt:

QUOTE: "Know thyself" - Temple of Apollo, Delphi
THEME: Classical Foundations
HEX: #1A237E

PROMPT:
"The concept of self-examination and philosophical inquiry 
visualized through a contemplative figure gazing into a 
mirror that reflects their inner essence as luminous 
geometric patterns, classical Renaissance painting meets 
modern digital art, marble textures, gold leaf accents, 
museum-quality dramatic lighting, ethereal contemplative 
atmosphere, fine art gallery quality, deep blue background 
(#1A237E), with warm gold accents, rich saturated tones, 
dramatic chiaroscuro, highly detailed, 8k resolution, 
professional art photography, sharp focus on central 
element, soft atmospheric depth --ar 2:3 --v 6 --s 250 --q 2"

Deliverable: 9 theme-specific prompt templates with examples

### Task 3.3: Generate First 25 Artworks

| Field | Details |
| --- | --- |
| Duration | 8 hours |
| Priority | 🔴 Critical |
| Dependencies | Prompt templates, approved quotes |

Specific Instructions:

Generation Workflow Per Artwork:

STEP 1: CONCEPT EXTRACTION (5 min)
├── Read quote 3 times
├── Identify core philosophical concept
├── Brainstorm 3-5 symbolic representations
└── Select most visually compelling symbol

STEP 2: PROMPT CONSTRUCTION (5 min)
├── Fill in concept block with extracted idea
├── Apply theme-specific color block
├── Add any quote-specific details
└── Compile complete prompt

STEP 3: INITIAL GENERATION (5 min)
├── Run prompt in Midjourney
├── Generate 4 variations
├── Wait for completion
└── Review all 4 outputs

STEP 4: EVALUATION (5 min)
├── Score each on Quality Scorecard:
│   □ Concept Clarity (1-10)
│   □ Aesthetic Quality (1-10)
│   □ Brand Alignment (1-10)
│   □ Emotional Resonance (1-10)
│   □ Technical Execution (1-10)
├── Total must be 35/50+ to accept
└── Select best OR proceed to iteration

STEP 5: ITERATION (If Needed - 10-15 min)
├── Round 2: Modify prompt based on learnings
├── Round 3: Significant restructure if needed
├── Maximum 3 rounds per artwork
└── If no acceptable result: Flag for review

STEP 6: FINALIZATION (5 min)
├── Select final version
├── Upscale to maximum resolution
├── Download high-resolution file
├── Rename: TM-[XXX]_[theme]_[keyword].png
└── Log in tracking spreadsheet

Quality Scorecard:

NFT QUALITY EVALUATION:

Concept Clarity         [___/10]
"Does it clearly convey the philosophical concept?"

Aesthetic Quality       [___/10]
"Is this gallery-worthy art?"

Brand Alignment         [___/10]
"Does it feel like a Turbomindz piece?"

Emotional Resonance     [___/10]
"Does it evoke contemplation/wonder?"

Technical Execution     [___/10]
"Resolution, composition, no artifacts?"

TOTAL: [___/50]

35+ = APPROVED
40+ = FEATURE PRIORITY
<35 = REGENERATE

Production Target for Week 3: - Generate: 35-40 images - Approve: 25 final selections - Distribute across themes: 2-3 per theme

Deliverable: 25 approved high-resolution artwork files with documentation

## 📅 WEEK 4: AI ART GENERATION (Part 2) & IPFS STORAGE

Objective: Complete initial 50 NFTs and upload to decentralized storage [2]

### Task 4.1: Generate Remaining 25 Artworks

| Field | Details |
| --- | --- |
| Duration | 8 hours |
| Priority | 🔴 Critical |
| Dependencies | Week 3 completion |

Specific Instructions: - Follow same workflow as Task 3.3 - Focus on themes underrepresented in first batch - Ensure variety across all 9 themes - Target: 5-6 pieces per theme for initial 50

Style Universe Rotation (Optional Variety): [1] Select from the 38 parallel universes for variety:

RECOMMENDED UNIVERSES FOR INITIAL DROP:

Universe 1: "Alchemical Renaissance" - Perfect brand alignment
Universe 3: "Floating Sumi-e Cosmos" - Eastern themes
Universe 7: "Crystalline Dreamscape" - High visual impact
Universe 12: "Persian Miniature Dreams" - Complex layering
Universe 18: "Vaporwave Antiquity" - Modern appeal

Deliverable: Additional 25 approved artwork files, total 50 complete

### Task 4.2: Set Up Pinata IPFS Account

| Field | Details |
| --- | --- |
| Duration | 30 minutes |
| Priority | 🔴 Critical |
| Dependencies | None |

Specific Instructions:

PINATA SETUP STEPS:

1. Go to pinata.cloud
2. Click "Sign Up" → Use email (not social login)
3. Verify email
4. Complete profile setup
5. Navigate to API Keys
6. Generate new API key:
   - Name: "Turbomindz-Production"
   - Permissions: pinFileToIPFS, pinJSONToIPFS
   - Save API Key and Secret securely
7. Test upload with sample file
8. Verify file accessible via IPFS gateway

Test URL Format:

https://gateway.pinata.cloud/ipfs/[YOUR-CID-HERE]

Deliverable: Active Pinata account with API credentials documented

### Task 4.3: Create Metadata JSON Files

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Approved artworks |

Specific Instructions:

Metadata JSON Template:

{
  "name": "TM-001: Know Thyself",
  "description": "\"Know thyself.\" — Inscribed at Temple of Apollo, Delphi (Ancient Greece)\n\nThis piece visualizes the foundational philosophical concept of self-examination through a contemplative figure gazing into a mirror that reflects inner essence as luminous geometric patterns.\n\nTheme: Classical Foundations\nCollection: Turbomindz Philosophical Art\nEdition: 1/1",
  "image": "ipfs://[CID-PLACEHOLDER]",
  "external_url": "https://turbomindz.xyz/nft/tm-001",
  "attributes": [
    {
      "trait_type": "Theme",
      "value": "Classical Foundations"
    },
    {
      "trait_type": "Author",
      "value": "Temple of Apollo, Delphi"
    },
    {
      "trait_type": "Era",
      "value": "Ancient Greece"
    },
    {
      "trait_type": "Collection Number",
      "value": 1
    },
    {
      "trait_type": "Total Supply",
      "value": 448
    },
    {
      "trait_type": "Art Style",
      "value": "Marble Renaissance Digital"
    },
    {
      "trait_type": "Marriage Status",
      "value": "Available"
    }
  ]
}

Required Attributes for All NFTs: | Attribute | Type | Description | |———–|——|————-| | Theme | String | One of 9 themes | | Author | String | Quote attribution | | Era | String | Time period | | Collection Number | Number | 1-448 | | Total Supply | Number | 448 | | Art Style | String | Default or Universe name | | Marriage Status | String | Available/Married |

Batch Creation Process: 1. Create template JSON file 2. Duplicate for each NFT 3. Fill in unique details from quote database 4. Validate JSON syntax (jsonlint.com) 5. Save as: tm-[XXX]-metadata.json

Deliverable: 50 validated JSON metadata files

### Task 4.4: Upload Images to IPFS

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Pinata account, finalized images |

Specific Instructions:

BATCH UPLOAD PROCESS:

1. Organize images in folder:
   /turbomindz-images/
   ├── TM-001_classical_know-thyself.png
   ├── TM-002_existentialism_absurd.png
   └── ... (all 50 images)

2. In Pinata dashboard:
   - Click "Upload"
   - Select "File"
   - Choose image
   - Click "Upload"
   - Wait for CID generation

3. Record CID in tracking sheet:
   | TM-ID | Image CID | Upload Date | Verified |
   |-------|-----------|-------------|----------|
   | TM-001| Qm...xxx  | 2025-01-15  | ✅       |

4. Verify each upload:
   - Open: https://gateway.pinata.cloud/ipfs/[CID]
   - Confirm image displays correctly
   - Check resolution and quality

5. Update metadata JSON files with actual CIDs:
   - Replace [CID-PLACEHOLDER] with actual CID
   - Format: "ipfs://[CID]"

Deliverable: All 50 images uploaded with CIDs recorded

### Task 4.5: Upload Metadata to IPFS

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Images uploaded, metadata updated |

Specific Instructions:

METADATA UPLOAD PROCESS:

1. Verify all JSON files have correct image CIDs
2. Validate JSON syntax for each file
3. Upload each metadata file to Pinata
4. Record metadata CID in tracking sheet:
   | TM-ID | Image CID | Metadata CID | Status |
   |-------|-----------|--------------|--------|
   | TM-001| Qm...xxx  | Qm...yyy     | Ready  |

5. Verify metadata resolves:
   - Open: https://gateway.pinata.cloud/ipfs/[MetadataCID]
   - Confirm JSON displays correctly
   - Verify image CID in JSON loads image

Final Verification Checklist:

□ All 50 image CIDs recorded
□ All 50 metadata CIDs recorded
□ All JSON files have correct image references
□ All IPFS links verified working
□ Backup of all files stored locally
□ Backup of CID tracking sheet exported

Deliverable: Complete IPFS upload with verification documentation

## 📅 WEEK 5: OPENSEA & DISCORD SETUP

Objective: Configure NFT marketplace and community platform [2]

### Task 5.1: Create OpenSea Collection

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Wallet created, images on IPFS |

Specific Instructions:

OPENSEA COLLECTION SETUP:

1. Go to opensea.io
2. Click "Connect Wallet" → MetaMask
3. Ensure on Polygon network
4. Click profile → "Create a collection"

COLLECTION SETTINGS:
├── Name: "Turbomindz Philosophical Art"
├── URL: turbomindz-philosophical-art
├── Description: [See below]
├── Category: Art > Philosophy
├── Links:
│   ├── Website: https://turbomindz.xyz
│   ├── Discord: [Discord invite link]
│   └── Twitter: [Twitter handle]
├── Creator Earnings: 5%
├── Blockchain: Polygon
└── Display Theme: Gallery

COLLECTION DESCRIPTION:
"Turbomindz transforms the most powerful quotes from 
history's greatest minds into museum-quality AI-generated 
art. Each NFT represents a unique philosophical insight 
visualized through the 'Marble Renaissance Digital' style.

🔮 Special Feature: Marriage System
Owners can permanently bind physical artworks to their 
NFTs, creating phygital assets with complete provenance.

📚 9 Philosophical Themes:
• Classical Foundations
• Enlightenment & Reason
• Existentialism & Modern
• Mysticism & Esoterica
• Eastern Wisdom
• Science, Media & Modernity
• Poetry, Aesthetics & Literature
• Civic, Social & Moral
• Psychology, Mind & Meaning

Total Collection: 448 unique pieces
Blockchain: Polygon (near-zero gas fees)

CREATE. CONNECT. TRADE FAIR."

Deliverable: Live OpenSea collection configured

### Task 5.2: Mint All 50 NFTs to Collection

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Collection created, metadata ready |

Specific Instructions:

NFT MINTING WORKFLOW (Per NFT):

1. In collection, click "Add item"
2. Upload image (or use IPFS link)
3. Fill details:
   ├── Name: [From metadata]
   ├── External link: [From metadata]
   ├── Description: [From metadata]
   └── Properties: [Add all attributes manually]

4. Add Properties (one by one):
   ├── Theme: [value]
   ├── Author: [value]
   ├── Era: [value]
   ├── Collection Number: [value]
   ├── Total Supply: 448
   ├── Art Style: [value]
   └── Marriage Status: Available

5. Supply: 1 (unique)
6. Blockchain: Polygon
7. Click "Create"
8. Sign transaction in MetaMask
9. Verify listing appears correctly
10. Record OpenSea URL in tracking sheet

BATCH EFFICIENCY TIP:
- Open multiple browser tabs
- Copy/paste descriptions
- Use keyboard shortcuts
- Batch similar themes together

Quality Control Checklist (Every 10 NFTs):

□ All properties display correctly
□ Images load properly
□ Descriptions are accurate
□ Theme colors consistent
□ Links functional
□ No typos in names

Deliverable: 50 NFTs minted and live on OpenSea

### Task 5.3: Discord Server Setup

| Field | Details |
| --- | --- |
| Duration | 3 hours |
| Priority | 🔴 Critical |
| Dependencies | None |

Specific Instructions:

DISCORD SERVER CREATION:

1. Create new server:
   - Click + in server list
   - "Create My Own"
   - "For a club or community"
   - Name: "Turbomindz"
   - Upload logo as icon

2. Enable Community Features:
   - Server Settings → Enable Community
   - Set #welcome as rules channel
   - Set #announcements as updates channel
   - Enable Community Welcome Screen

3. Enable Forum Channels:
   - Already enabled with Community features
   - Essential for marketplace structure

Channel Structure to Create: [2]

📢 INFORMATION (Public - Everyone can view)
├── #welcome (Read-only)
├── #rules-and-charter (Read-only)
├── #announcements (Read-only)
└── #roadmap-updates (Read-only)

🏪 MARKETPLACE (Token-Gated - Forum Channels)
├── 📂 #paintings-drawings
├── 📂 #sculpture-3d
├── 📂 #digital-generative
├── 📂 #photography-editions
├── 📂 #prints-multiples
├── 📂 #books-zines-manuscripts
├── 📂 #craft-design-wearables
├── 📂 #calligraphy-lettering-type
├── 📂 #commissions-collaborations
└── 📂 #services-studio-support

📜 THE REGISTRY (Token-Gated - Forum Channels)
├── #registry-how-to (Regular channel)
├── 📂 #marriage-requests (Forum)
├── #verified-marriages (Read-only archive)
└── #completed-deals (Read-only archive)

📚 THEMES & DISCUSSION (Token-Gated)
├── 📂 #classical-foundations
├── 📂 #enlightenment-reason
├── 📂 #existentialism-modern
├── 📂 #mysticism-esoterica
├── 📂 #eastern-wisdom
├── 📂 #science-media-modernity
├── 📂 #poetry-aesthetics-literature
├── 📂 #civic-social-moral
└── 📂 #psychology-mind-meaning

⚖️ GOVERNANCE (Token-Gated)
├── #proposals
├── #voting-announcements
├── #tribunal-cases
├── #transparency-reports
└── #provenance-help-desk

🎓 EDUCATION & GROWTH
├── #work-in-progress-critique
├── #tools-tech-nfts
├── #legal-ip-learning
├── #success-mindset
├── #introductions-studio-tours
└── #forum-feedback

🆘 SUPPORT
├── #help-questions
├── #technical-support
└── #report-issues

Deliverable: Complete Discord server with all channels

### Task 5.4: Configure Forum Channel Tags

| Field | Details |
| --- | --- |
| Duration | 1 hour |
| Priority | 🔴 Critical |
| Dependencies | Forum channels created |

Specific Instructions:

Marketplace Forum Tags:

In each marketplace forum channel, add these tags:

TAG: [FS]
├── Color: Green
├── Description: For Sale - Active listing
└── Emoji: 💰

TAG: [IC]
├── Color: Yellow
├── Description: Interest Check - Testing demand
└── Emoji: 🤔

TAG: [AUCTION]
├── Color: Purple
├── Description: Time-limited bidding
└── Emoji: 🔨

TAG: [SOLD]
├── Color: Gray
├── Description: Transaction complete
└── Emoji: ✅

TAG: [WTB/WTT]
├── Color: Blue
├── Description: Want to Buy/Trade
└── Emoji: 🔍

TAG: [PROVENANCE]
├── Color: Gold
├── Description: Authentication request
└── Emoji: 📜

TAG: [COA]
├── Color: Gold
├── Description: Certificate of Authenticity included
└── Emoji: 🏆

TAG: [SHIPPING]
├── Color: Orange
├── Description: Shipping/logistics discussion
└── Emoji: 📦

Marriage Registry Tags:

TAG: Pending
├── Color: Yellow
└── Description: Awaiting verification

TAG: Verified
├── Color: Green
└── Description: Marriage confirmed

TAG: [Art Type Tags - one for each marketplace category]

Deliverable: All forum channels with complete tag systems

## 📅 WEEK 6: TOKEN GATING & GOVERNANCE

Objective: Implement verification and voting systems [2]

### Task 6.1: Guild.xyz Integration

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Discord server, OpenSea collection |

Specific Instructions:

GUILD.XYZ SETUP:

1. Go to guild.xyz
2. Connect wallet (same as OpenSea)
3. Click "Create Guild"
4. Guild Settings:
   ├── Name: Turbomindz
   ├── Description: Philosophical art community
   └── Logo: Brand logo

5. Connect to Discord:
   ├── Add Guild.xyz bot to server
   ├── Grant required permissions
   └── Select server

6. Create Role Requirements:

ROLE: @Member
├── Requirement: Hold 1+ Turbomindz NFT
├── Logic: "Any" from collection
├── Contract: [OpenSea collection address]
├── Blockchain: Polygon
└── Discord Role: Member

ROLE: @Collector (Tier 2)
├── Requirement: Hold 3+ Turbomindz NFTs
└── Discord Role: Collector

ROLE: @Patron (Tier 3)
├── Requirement: Hold 5+ Turbomindz NFTs
└── Discord Role: Patron

7. Set Channel Permissions:
   ├── Marketplace channels: @Member required
   ├── Registry channels: @Member required
   ├── Theme rooms: @Member required
   ├── Governance: @Member required
   └── Public channels: Everyone

8. Add "Verify" button:
   ├── In #welcome channel
   ├── Configure verify widget
   └── Test with test wallet

Testing Protocol:

1. Use secondary wallet
2. Purchase test NFT (or transfer one)
3. Click verify button
4. Connect wallet via Guild.xyz
5. Confirm @Member role assigned
6. Verify access to gated channels
7. Document any issues

Deliverable: Working token-gated Discord with Guild.xyz

### Task 6.2: Snapshot.org Space Setup

| Field | Details |
| --- | --- |
| Duration | 1 hour |
| Priority | 🟡 Important |
| Dependencies | Guild.xyz working |

Specific Instructions:

SNAPSHOT SETUP:

1. Go to snapshot.org
2. Connect wallet
3. Click "Create a space"

SPACE SETTINGS:
├── Name: Turbomindz
├── Symbol: TMIND
├── Network: Polygon
├── Avatar: Brand logo
├── Description: "Community governance for 
│   Turbomindz philosophical art collective"
└── Terms: Link to Charter

STRATEGIES:
├── Strategy: erc721
├── Contract: [OpenSea collection address]
├── Network: 137 (Polygon)
└── Weight: 1 NFT = 1 vote

VOTING SETTINGS:
├── Voting Period: 7 days
├── Quorum: 10% of circulating supply
├── Proposal Threshold: 10 supporters
└── Validation: Basic

MEMBERS:
├── Add admins: [Your addresses]
└── Controllers: Core team wallets

Test Proposal:

Create test proposal:
- Title: "[TEST] Snapshot Configuration Test"
- Description: "Testing voting functionality"
- Type: Single choice
- Choices: "Yes", "No", "Abstain"
- Duration: 1 day
- Vote with your wallet
- Verify vote registers correctly

Deliverable: Active Snapshot space with test vote completed

### Task 6.3: Create Role & Badge Structure

| Field | Details |
| --- | --- |
| Duration | 1 hour |
| Priority | 🟡 Important |
| Dependencies | Discord server configured |

Specific Instructions:

Discord Roles to Create: [2]

COMMUNITY ROLES (Color-coded):

@Founder (Gold #C9A227)
├── Permissions: Administrator
└── Manually assigned

@Elder (Purple #4A148C)
├── Permissions: Moderate members, manage messages
├── Requirements: Elected via Snapshot
└── Number: 5-7 members

@Scribe (Teal #00838F)
├── Permissions: Manage threads, add reactions
├── Requirements: Trained and approved
└── Number: 3-5 members

@Patron (Blue #1A237E)
├── Permissions: Standard + priority support
├── Requirements: 5+ NFTs (Guild.xyz)
└── Automatic via token gate

@Collector (Green #00695C)
├── Permissions: Standard
├── Requirements: 3+ NFTs (Guild.xyz)
└── Automatic via token gate

@Member (Default color)
├── Permissions: Standard access
├── Requirements: 1+ NFT (Guild.xyz)
└── Automatic via token gate

@Visitor (Gray)
├── Permissions: View public channels only
└── Default for unverified

Achievement Badges (Roles):

⭐ @Trusted Seller
├── Requirements: 5+ trades, 0 disputes
└── Manually awarded by Scribes

💍 @First Marriage
├── Requirements: Completed first marriage
└── Manually awarded

🤝 @Deal Maker
├── Requirements: Completed first trade
└── Manually awarded

📜 @Charter Contributor
├── Requirements: Helped draft Charter
└── Manually awarded

Deliverable: Complete role hierarchy in Discord

## 📅 WEEK 7: DOCUMENTATION & CHARTER

Objective: Complete all governance and operational documents [2]

### Task 7.1: Finalize Turbomindz Charter

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Role structure, processes defined |

Specific Instructions:

Charter Structure: [2]

THE TURBOMINDZ CHARTER
A Social Contract for Fair Trade, Honest Discourse, 
and Creative Community

PREAMBLE
[Mission statement and community values]

ARTICLE I: THE MARRIAGE PACT
Section 1.1: Definition
Section 1.2: Documentation Requirements
Section 1.3: Verification Process
Section 1.4: Permanence & Dissolution

ARTICLE II: THE OPEN MARKET
Section 2.1: Public Negotiation Requirement
Section 2.2: Thread Tag Requirements
Section 2.3: Prohibited Communications
Section 2.4: Price Transparency

ARTICLE III: THE SHIPPING COVENANT
Section 3.1: Seller Obligations by Art Type
Section 3.2: Buyer Obligations
Section 3.3: Timeline Requirements
Section 3.4: Insurance Requirements

ARTICLE IV: THE TRIBUNAL
Section 4.1: Elder Eligibility
Section 4.2: Selection Process
Section 4.3: Evidence & Deliberation
Section 4.4: Remedies Available

ARTICLE V: GOVERNANCE
Section 5.1: Voting Rights
Section 5.2: Proposal Process
Section 5.3: Thresholds
Section 5.4: Charter Amendments

ARTICLE VI: ENFORCEMENT & EXILE
Section 6.1: Strike System
Section 6.2: Exile Process
Section 6.3: Appeal Rights

ARTICLE VII: ROLES & RESPONSIBILITIES
[Define each role]

ARTICLE VIII: CONTENT & IP GUIDELINES
[Public domain requirements, theme room rules]

ARTICLE IX: DISCLAIMERS
[Liability limitations, not financial advice]

SIGNATURES & EFFECTIVE DATE

Deliverable: Complete Charter document (15-20 pages)

### Task 7.2: Create Marriage Documentation Guide

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Charter marriage section |

Specific Instructions:

Marriage Guide Contents:

TURBOMINDZ MARRIAGE GUIDE
How to Bind Physical Art to Your NFT

OVERVIEW
- What is Marriage?
- Why Marriage matters
- Permanence explained

REQUIREMENTS CHECKLIST

□ PHOTO REQUIREMENTS (4-6 photos)
├── Minimum 2000 pixels on longest edge
├── Front view with good lighting
├── Back view showing any details
├── 2+ detail shots of important features
├── Size reference with ruler
└── Any damage/wear documented

□ VIDEO REQUIREMENTS (20-60 seconds)
├── Continuous recording (NO CUTS!)
├── Shows today's date on paper
├── Shows your Discord username on paper
├── Shows NFT number on paper
├── Full artwork visible in frame
└── Your username spoken aloud

□ DESCRIPTION REQUIREMENTS
├── Title of artwork
├── Art TYPE (must match marketplace category)
├── Medium (oil, acrylic, print, etc.)
├── Dimensions (height x width x depth)
├── Condition rating (Excellent/Good/Fair/Poor)
├── Provenance information
├── Shipping origin location
└── Any restrictions noted

SUBMISSION PROCESS
Step 1: Go to #marriage-requests
Step 2: Create new thread
Step 3: Title: "Marriage Request - NFT #XX"
Step 4: Select art type tag
Step 5: Upload photos
Step 6: Upload or link video
Step 7: Post description
Step 8: Wait for Scribe review (48 hours)

VERIFICATION OUTCOMES
✅ VERIFIED - Marriage approved, moved to archive
❌ CORRECTIONS NEEDED - Scribe explains what's missing
⏸️ ON HOLD - Additional information requested

FAQ
[Common questions and answers]

Deliverable: Complete Marriage Guide (PDF + Discord post)

### Task 7.3: Create Trading & Shipping Guides

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Charter trading sections |

Specific Instructions:

Trading Guide Contents:

TURBOMINDZ TRADING GUIDE

CREATING A LISTING

1. Choose correct marketplace category
2. Create thread with proper tag [FS]
3. Include all required information:

LISTING TEMPLATE:
────────────────────────────────────
[FS] NFT #XX + [Art Type] Description

Quote: "[Quote text]"
Attribution: [Author]
Theme: [Theme name]

NFT Status: [Available/Listed]
Marriage Status: [Yes with link / No]

If Married:
- Art Type: [Category]
- Title: [Artwork title]
- Medium: [Materials]
- Size: [Dimensions]
- Condition: [Rating]
- [COA]: [Yes/No]
- [PROVENANCE]: [Link to marriage thread]

ASKING PRICE: $[Total] (All-inclusive)
- NFT: $[Amount]
- [SHIPPING] USA: $[Amount]
- [SHIPPING] International: $[Amount]
- Insurance: [Included for >$200]

Open to offers!
────────────────────────────────────

NEGOTIATION RULES
- All offers in public thread
- NO private DM negotiations
- Clear "OFFER:" and "COUNTER:" language
- "AGREED" signals acceptance
- Share wallet address after agreement

EXECUTION STEPS
1. Seller creates private OpenSea listing
2. Buyer completes purchase
3. Buyer posts "PAID" in thread
4. Seller ships within 72 hours
5. Seller posts tracking with [SHIPPING] tag
6. Buyer posts unboxing video
7. Buyer confirms "RECEIVED"
8. Thread updated to [SOLD]

Shipping Standards by Art Type: [2]

PAINTINGS & DRAWINGS
├── Glassine interleaf
├── Acid-free tissue padding
├── Rigid cardboard corners
├── Double-box for framed
└── "FRAGILE" labels

SCULPTURE & 3D
├── Custom foam inserts
├── Multiple layers of protection
├── Sturdy outer box
├── Insurance mandatory >$100
└── Photo documentation of packing

PHOTOGRAPHY & PRINTS
├── Acid-free tissue
├── Rigid mailer or flat box
├── "DO NOT BEND" labels
└── Humidity protection

BOOKS & ZINES
├── Bubble wrap
├── Rigid mailer
├── Moisture protection
└── Corner protection

DIGITAL/GENERATIVE
├── USB/drive in padded envelope
├── Include digital backup link
└── Certificate of authenticity

CRAFT & WEARABLES
├── Appropriate to item type
├── Tissue for delicates
└── Sturdy box

Deliverable: Trading Guide + Shipping Standards (PDF + Discord posts)

### Task 7.4: Create FAQ Document

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🟡 Important |
| Dependencies | All other documentation |

Specific Instructions:

FAQ Categories:

TURBOMINDZ FAQ

SECTION 1: UNDERSTANDING TURBOMINDZ
Q: What is Turbomindz?
Q: What makes Turbomindz different?
Q: Why philosophical quotes?
Q: What is the "Marriage" system?

SECTION 2: GETTING STARTED
Q: How do I buy my first NFT?
Q: What wallet do I need?
Q: Why Polygon instead of Ethereum?
Q: How do I join the Discord?
Q: How does verification work?

SECTION 3: THE MARKETPLACE
Q: How are categories organized?
Q: What do the thread tags mean?
Q: Can I negotiate prices?
Q: Why must negotiations be public?

SECTION 4: MARRIAGE SYSTEM
Q: What does Marriage mean?
Q: Is Marriage reversible?
Q: What documentation do I need?
Q: How long does verification take?

SECTION 5: TRADING & SHIPPING
Q: What's included in the price?
Q: Who pays for shipping?
Q: What if my item arrives damaged?
Q: What's the return policy?

SECTION 6: DISPUTES & GOVERNANCE
Q: What if something goes wrong?
Q: Who are the Elders?
Q: How do I vote on proposals?
Q: Can I be banned?

SECTION 7: TECHNICAL
Q: Where are NFTs stored?
Q: What are gas fees on Polygon?
Q: Is my data private?

Deliverable: Comprehensive FAQ (40+ questions)

## 📅 WEEK 8: TEAM BUILDING & SYSTEM TESTING

Objective: Recruit team, test all systems end-to-end [2]

### Task 8.1: Recruit Volunteer Scribes

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Documentation complete |

Specific Instructions:

Scribe Requirements:

IDEAL SCRIBE PROFILE:
- Active in art/NFT communities
- Reliable availability (5-10 hrs/week)
- Good written communication
- Detail-oriented
- Comfortable with Discord moderation
- Interest in philosophy/art

SCRIBE RESPONSIBILITIES:
- Verify Marriage requests (48hr turnaround)
- Monitor marketplace threads
- Answer basic support questions
- Escalate complex issues
- Maintain documentation accuracy

Recruitment Process: 1. Post in relevant Discord servers/Twitter 2. Review applications 3. Conduct brief interview (voice chat) 4. Provide training materials 5. Shadow period (1 week) 6. Full access granted

Scribe Application Form:

1. Discord username:
2. Time zone:
3. Hours available per week:
4. Experience with Discord moderation:
5. Interest in philosophy/art:
6. Why do you want to help Turbomindz?
7. Example: How would you handle a 
   Marriage request with missing photos?

Deliverable: 2-3 trained Scribes ready for launch

### Task 8.2: Scribe Training Program

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Scribes recruited |

Specific Instructions:

Training Curriculum:

SESSION 1: TURBOMINDZ OVERVIEW (1 hour)
- Mission and values
- Community structure
- Role of Scribes
- Charter overview

SESSION 2: MARRIAGE VERIFICATION (1.5 hours)
- Documentation requirements
- Photo quality assessment
- Video verification checklist
- Common issues and solutions
- Practice with mock submissions

SESSION 3: MARKETPLACE MODERATION (1 hour)
- Thread tag system
- Listing requirements
- Identifying rule violations
- Escalation procedures

SESSION 4: SUPPORT & COMMUNICATION (30 min)
- Tone and voice guidelines
- Common questions
- When to escalate
- Documentation practices

Scribe Checklist Template:

MARRIAGE VERIFICATION CHECKLIST

OWNERSHIP CHECK:
□ Wallet owns claimed NFT (verify on OpenSea)
□ NFT not already married (check registry)
□ Thread properly formatted

PHOTO REVIEW:
□ Resolution adequate (2000px+)
□ Front view present and clear
□ Back view present
□ Detail shots present (2+)
□ Size reference included
□ Condition accurately shown

VIDEO REVIEW:
□ Continuous recording (no cuts)
□ Date visible on paper
□ Discord username visible
□ NFT number visible
□ Full artwork in frame
□ Username spoken aloud

DESCRIPTION REVIEW:
□ Title provided
□ Art TYPE matches category
□ Medium stated
□ Dimensions included
□ Condition rated
□ Shipping origin stated

DECISION:
□ All requirements met → ✅ VERIFIED
□ Missing items → Request corrections (72hr deadline)
□ Suspicious → Escalate to senior team

Deliverable: Trained Scribes with documented competency

### Task 8.3: Run Mock Marriages

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Scribes trained |

Specific Instructions:

Mock Marriage Test Protocol:

TEST SCENARIO 1: Perfect Submission
- Submit complete documentation
- All requirements met
- Expected outcome: Approved in <48hrs
- Verify: Thread moved correctly, tags applied

TEST SCENARIO 2: Missing Photos
- Submit with only 2 photos
- Expected outcome: Correction request
- Verify: Clear explanation of what's needed

TEST SCENARIO 3: Video Missing Elements
- Submit video without visible date
- Expected outcome: Correction request
- Verify: Specific feedback provided

TEST SCENARIO 4: Wrong Art Category
- Submit painting in sculpture category
- Expected outcome: Correction request
- Verify: Scribe identifies and guides

TEST SCENARIO 5: Edge Case - Multiple Items
- Submit married collection (3 pieces)
- Expected outcome: Guidance provided
- Verify: Scribe handles appropriately

Documentation: - Record all test results - Note any process improvements needed - Update guides based on findings

Deliverable: All mock tests passed, processes refined

### Task 8.4: Run Mock Trades

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Marketplace channels configured |

Specific Instructions:

Mock Trade Test Protocol:

TEST SCENARIO 1: Simple Sale
- Seller: List item with [FS] tag
- Buyer: Make offer in thread
- Negotiate: Counter-offer exchange
- Agreement: Clear AGREED statements
- Execution: Mock OpenSea private sale
- Shipping: Post mock tracking
- Receipt: Post mock confirmation
- Completion: Update to [SOLD]

TEST SCENARIO 2: Interest Check → Sale
- Post [IC] thread
- Gather interest
- Convert to [FS]
- Complete sale

TEST SCENARIO 3: Auction Format
- Post [AUCTION] with rules
- Multiple bids
- Winner determination
- Completion

TEST SCENARIO 4: Buyer Withdrawal
- Agreement made
- Buyer backs out
- Document handling procedure

TEST SCENARIO 5: Shipping Dispute (Mock)
- Claim damage on arrival
- Open dispute process
- Elder panel simulation
- Resolution documentation

Deliverable: All trade scenarios tested, processes verified

### Task 8.5: End-to-End System Test

| Field | Details |
| --- | --- |
| Duration | 3 hours |
| Priority | 🔴 Critical |
| Dependencies | All previous tasks |

Specific Instructions:

Complete Flow Test:

TEST: NEW USER JOURNEY

1. DISCOVERY
   □ Find project via social/OpenSea
   □ View collection on OpenSea
   □ Read website/landing page

2. PURCHASE
   □ Connect wallet to OpenSea
   □ Switch to Polygon network
   □ Purchase NFT
   □ Verify NFT in wallet

3. VERIFICATION
   □ Join Discord
   □ Click Guild.xyz verify button
   □ Connect wallet
   □ Receive @Member role
   □ Access gated channels

4. COMMUNITY ENGAGEMENT
   □ Read #rules-and-charter
   □ Introduce in #introductions
   □ Browse marketplace
   □ Join theme room discussion

5. MARRIAGE (if applicable)
   □ Prepare documentation
   □ Submit in #marriage-requests
   □ Receive verification
   □ Confirm in registry

6. TRADING
   □ Create listing (or make offer)
   □ Negotiate in public
   □ Complete transaction
   □ Confirm receipt

7. GOVERNANCE
   □ View active proposals
   □ Cast vote via Snapshot
   □ Verify vote recorded

Issue Log Template:

| Step | Expected | Actual | Status | Fix Required |
|------|----------|--------|--------|--------------|
| 3.3  | Role in 30s | 2 minutes | ⚠️ | Monitor |
| 5.1  | Clear info | Confusing | ❌ | Rewrite |

Deliverable: System test report with all issues resolved

# PHASE 2: PRE-LAUNCH MARKETING (Weeks 9-12)

## 📅 WEEK 9: WEBSITE BUILD

Objective: Launch public-facing website [2]

### Task 9.1: Website Development (Carrd)

| Field | Details |
| --- | --- |
| Duration | 6 hours |
| Priority | 🔴 Critical |
| Dependencies | Brand assets, copy |

Specific Instructions:

Website Sections: [2]

TURBOMINDZ WEBSITE STRUCTURE:

1. HERO SECTION
   ├── Headline: "Where Wisdom Meets Canvas"
   ├── Subheadline: Collection description
   ├── Primary CTA: "Enter Community" → Discord
   ├── Secondary CTA: "View Collection" → OpenSea
   └── Background: Brand imagery/animation

2. HOW IT WORKS (3 Steps)
   ├── Step 1: COLLECT - Acquire digital art
   ├── Step 2: MARRY - Bind to physical
   └── Step 3: TRADE - Exchange openly

3. THE MARKETPLACE
   ├── Category showcase (10 types)
   └── CTA: Browse Marketplace → Discord

4. EXPLORE THEMES
   ├── Theme room showcase (9 themes)
   └── CTA: Join Discussion → Discord

5. THE REGISTRY
   ├── Marriage explanation
   └── CTA: Learn About Marriage

6. THE HONOR SYSTEM
   ├── Governance explanation
   └── CTA: Read Charter

7. MANIFESTO / ABOUT
   ├── Mission statement
   └── Full about us copy

8. FAQ (Accordion)
   ├── Key questions (6-10)
   └── Link to full FAQ

9. FOOTER
   ├── Social links
   ├── Legal links
   └── Copyright

Carrd Setup: 1. Create Carrd account (Pro: $19/year) 2. Start with blank template 3. Add sections per structure 4. Upload brand images 5. Add copy from documentation 6. Configure mobile responsiveness 7. Connect custom domain 8. Add Google Analytics (optional)

Deliverable: Live website at turbomindz.xyz

## 📅 WEEK 10: CONTENT & DESIGN ASSETS

Objective: Create all visual assets for launch [2] [4]

### Task 10.1: Social Media Templates

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🟡 Important |
| Dependencies | Brand style guide |

Specific Instructions:

Templates Needed:

TEMPLATE SET:

1. NFT Feature Card (1080x1350 - Instagram)
   - NFT image
   - Quote text overlay
   - Theme indicator
   - TM-number

2. Quote Card (1080x1080 - Square)
   - Quote text prominent
   - Attribution
   - Brand footer

3. Announcement (1080x1350)
   - Headline space
   - Body text area
   - CTA

4. Story Template (1080x1920)
   - Multiple variants
   - Swipe-up CTA area

5. Twitter Header (1500x500)
   - Brand imagery
   - Tagline

6. Discord Banner (960x540)
   - Server branding

Tool: Canva (Free) - Create template set - Use brand colors/fonts - Save as team templates - Export masters in multiple formats

Deliverable: Complete template set in Canva

### Task 10.2: Character Marketing Graphics [4] [5]

| Field | Details |
| --- | --- |
| Duration | 6 hours |
| Priority | 🟡 Important |
| Dependencies | Character designs |

Specific Instructions:

Generate Cosmo & Nova Graphics:

Hero Image Prompt:

Cosmo the astronaut and Nova the alien standing together 
as best friends waving hello at the viewer, claymation 
stop-motion animation style, Cosmo is cute chibi character 
with large head wearing smooth matte white spacesuit with 
bright orange boots orange gloves orange knee pads and 
orange backpack, large spherical fishbowl helmet showing 
friendly face with big round eyes rosy cheeks warm smile, 
Nova is small floating alien with large smooth dome head 
bright cyan teal skin with gold bioluminescent vein patterns, 
huge glowing golden amber almond eyes, three-fingered hands 
with gold tips, futuristic cosmic environment with neon-lit 
alien landscape floating platforms, smooth plasticine material 
with fingerprint textures, Pixar meets Aardman quality, 
shot with Nikon D850 DSLR Nikkor 24-70mm f/2.8 lens, 
professional studio lighting --ar 16:9 --v 7 --s 250 --q 2

Scene Variations to Generate: 1. Welcome/Greeting 2. Teaching/Explaining 3. Celebrating 4. Pointing/Presenting 5. Trading visualization 6. Marriage ceremony 7. Community gathering

Deliverable: 10+ character marketing images

### Task 10.3: 30-Day Content Calendar

| Field | Details |
| --- | --- |
| Duration | 3 hours |
| Priority | 🔴 Critical |
| Dependencies | Templates, NFT images |

Specific Instructions:

Content Calendar Structure:

WEEK 1: Awareness
├── Day 1: Launch announcement
├── Day 2: What is Turbomindz?
├── Day 3: Meet Cosmo & Nova
├── Day 4: Featured NFT #1
├── Day 5: Marriage system explained
├── Day 6: Community values
└── Day 7: Week recap

WEEK 2: Education
├── Day 8: Theme spotlight (Classical)
├── Day 9: Featured NFT #2
├── Day 10: How to buy guide
├── Day 11: Theme spotlight (Existentialism)
├── Day 12: Featured NFT #3
├── Day 13: Trading explained
└── Day 14: Community spotlight

WEEK 3: Engagement
├── Day 15: Philosophy Challenge launch
├── Day 16: Featured NFT #4
├── Day 17: Theme spotlight (Eastern)
├── Day 18: Quote of the day
├── Day 19: Featured NFT #5
├── Day 20: Member testimonial
└── Day 21: Week recap

WEEK 4: Momentum
├── Day 22: Stats/transparency report
├── Day 23: Featured NFT #6
├── Day 24: Theme spotlight (Mysticism)
├── Day 25: Quote carousel
├── Day 26: Behind the scenes
├── Day 27: Community growth
└── Day 28-30: Month recap + next month preview

Deliverable: Complete 30-day content calendar with all copy/images

## 📅 WEEK 11: SOCIAL MEDIA LAUNCH

Objective: Establish social presence and begin audience building [2]

### Task 11.1: Account Setup & Profile Optimization

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Brand assets |

Specific Instructions:

Twitter/X Setup:

Username: @TurbomindzNFT
Display Name: Turbomindz | Philosophical Art 🧠
Bio: "Where wisdom meets canvas. AI-crafted philosophical 
art meets physical ownership. 448 unique pieces. 
CREATE. CONNECT. TRADE FAIR."
├── Location: The Digital Canvas
├── Website: turbomindz.xyz
├── Header: Brand banner
├── Avatar: Logo icon
└── Pinned: Launch announcement

Instagram Setup:

Username: @turbomindz
Display Name: Turbomindz | Art That Thinks 🖼️
Bio: "Philosophical wisdom × AI art × Physical ownership
✨ 448 unique NFTs
🎨 Marriage: Digital soul + Physical body
🔗 Join: [link in bio]"
├── Profile: Logo icon
├── Highlights: How It Works | Collection | Community | FAQ
└── Link: Linktree or bio link page

Deliverable: Optimized social profiles ready for launch

### Task 11.2: Launch Content Push

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Accounts set up, content ready |

Specific Instructions:

Launch Week Content Schedule:

LAUNCH DAY:
├── 08:00: Tweet - "Today we launch..."
├── 10:00: Instagram post - Main announcement
├── 12:00: Tweet - Thread explaining concept
├── 14:00: Instagram Story - Behind the scenes
├── 16:00: Tweet - First featured NFT
├── 18:00: Instagram Story - How to join
└── 20:00: Tweet - Day recap + community invite

DAY 2-7:
├── 3 tweets per day (educational, NFT feature, engagement)
├── 1 Instagram post per day
├── Daily stories
└── Community engagement (reply to all comments)

Deliverable: Launched social presence with active engagement

## 📅 WEEK 12: COMMUNITY BUILDING

Objective: Build pre-launch community of 200+ members [2]

### Task 12.1: Discord Soft Open

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Discord fully configured |

Specific Instructions:

Soft Launch Protocol:

1. Create limited invite (100 uses)
2. Share with:
   ├── Twitter followers
   ├── Early supporters
   └── Target communities

3. Welcome each member personally

4. Encourage:
   ├── Introductions
   ├── Feedback on structure
   └── Questions

5. Monitor and adjust based on feedback

6. Document common questions for FAQ updates

Deliverable: 50+ members in Discord during soft launch

### Task 12.2: Twitter Spaces Event

| Field | Details |
| --- | --- |
| Duration | 2 hours (prep + live) |
| Priority | 🟡 Important |
| Dependencies | Social presence established |

Specific Instructions:

Twitter Space: “AMA - Introducing Turbomindz”

PREPARATION:
├── Schedule Space 48 hours in advance
├── Promote across all channels
├── Prepare talking points
├── Invite co-hosts/guests

AGENDA (60 min):
├── 0-5: Welcome and introduction
├── 5-15: What is Turbomindz?
├── 15-25: The Marriage concept
├── 25-35: Community and governance
├── 35-55: Q&A from audience
└── 55-60: How to join + CTA

POST-EVENT:
├── Thank attendees on Twitter
├── Share recording (if available)
├── Follow up on unanswered questions
└── Document insights for improvement

Deliverable: Completed Twitter Space with recording

### Task 12.3: Whitelist Campaign

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🟡 Important |
| Dependencies | Community presence |

Specific Instructions:

Whitelist Structure:

WHITELIST BENEFITS:
├── Early access (24 hours before public)
├── Guaranteed mint slot
└── Discounted price (optional)

QUALIFICATION CRITERIA:
├── Join Discord
├── Introduce yourself
├── Engage in theme discussions
├── Follow on Twitter
└── Retweet launch announcement

WHITELIST TRACKING:
├── Create Google Form for applications
├── Review and approve manually
├── Announce approved members
└── Create whitelist role in Discord

TARGET: 100 whitelist spots

Deliverable: 100+ qualified whitelist registrations

# PHASE 3: LAUNCH (Weeks 13-16)

## 📅 WEEK 13: FINAL PREPARATIONS

Objective: Complete all launch readiness checks [2]

### Task 13.1: Final System Verification

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | All previous tasks |

Specific Instructions:

Launch Readiness Checklist:

TECHNICAL SYSTEMS:
□ All 50 NFTs visible on OpenSea
□ Metadata displays correctly
□ All IPFS links working
□ Prices set correctly
□ Royalty configured (5%)

DISCORD:
□ All channels functional
□ Guild.xyz verification working
□ Scribes ready and online
□ Welcome message updated
□ Charter posted

WEBSITE:
□ All links working
□ Mobile responsive
□ Analytics tracking
□ OpenSea link correct
□ Discord link correct

SOCIAL:
□ All profiles optimized
□ Content scheduled
□ Response templates ready
□ Team members briefed

TEAM:
□ Scribes have access
□ Support schedule confirmed
□ Escalation procedures clear
□ Communication channel active

Deliverable: All checklist items verified ✅

### Task 13.2: Team Launch Briefing

| Field | Details |
| --- | --- |
| Duration | 1 hour |
| Priority | 🔴 Critical |
| Dependencies | Team assembled |

Specific Instructions:

Briefing Agenda:

LAUNCH BRIEFING (60 min)

1. Launch Timeline (10 min)
   - Exact times for each action
   - Who does what

2. Responsibilities (15 min)
   - Community support
   - Technical issues
   - Social media monitoring
   - Escalation paths

3. Common Scenarios (15 min)
   - "How do I buy?"
   - "Verification not working"
   - "Can't see channels"
   - Troubleshooting steps

4. Emergency Protocols (10 min)
   - Major technical failure
   - Security incident
   - Community crisis
   - Communication tree

5. Q&A (10 min)
   - Team questions
   - Clarifications

Deliverable: Team aligned and ready

### Task 13.3: Content Pre-Scheduling

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🟡 Important |
| Dependencies | Content calendar |

Specific Instructions:

Pre-Schedule Launch Week Content:

TOOLS:
├── Later (free plan) - Instagram scheduling
├── TweetDeck - Twitter scheduling
└── Buffer (alternative)

SCHEDULE:
├── Launch day: All posts ready
├── Days 2-7: All posts scheduled
├── Stories: Templates ready for real-time
└── Discord: Announcement drafts ready

PREPARE:
├── Copy/paste ready responses
├── FAQ links bookmarked
├── Image assets accessible
└── Team notification system ready

Deliverable: All launch week content scheduled

## 📅 WEEK 14: 🚀 MINT LAUNCH

Objective: Successfully launch NFT collection [2]

### Task 14.1: Launch Day Execution

| Field | Details |
| --- | --- |
| Duration | Full day |
| Priority | 🔴 Critical |
| Dependencies | All preparations |

Specific Instructions:

Launch Day Schedule:

LAUNCH DAY TIMELINE:

06:00 - Wake up, final checks
07:00 - Team sync call
08:00 - Final system verification
09:00 - Go/no-go decision

10:00 - 🚀 LAUNCH
├── Enable public NFT sales on OpenSea
├── Post Discord announcement
├── Post Twitter announcement
├── Post Instagram announcement
├── Update website CTA

10:00-18:00 - Active Support Mode
├── Monitor sales activity
├── Welcome new members
├── Answer questions immediately
├── Document issues
├── Celebrate purchases publicly

18:00 - Midday team sync
├── Review progress
├── Address any issues
├── Plan evening activities

20:00 - Day wrap-up
├── Post day recap
├── Thank community
├── Share stats

22:00 - Team debrief
├── What went well
├── What to improve
├── Tomorrow priorities

Response Templates:

PURCHASE CONGRATULATION:
"🎉 Welcome to the village, [name]! You now own TM-[#]: 
[Title]. This piece explores [brief description]. Don't 
forget to verify in Discord to access the community!"

SUPPORT RESPONSE:
"Thanks for reaching out! [Answer]. Let me know if you 
have any other questions - we're here to help!"

VERIFICATION HELP:
"To verify: 1) Make sure you're in the Turbomindz Discord
2) Go to #welcome 3) Click the verification button 
4) Connect the wallet holding your NFT. Should take 
about 30 seconds!"

Deliverable: Successful launch day completed

### Task 14.2: Post-Launch Days 1-3

| Field | Details |
| --- | --- |
| Duration | Ongoing |
| Priority | 🔴 Critical |
| Dependencies | Launch completed |

Specific Instructions:

Days 1-3 Focus Areas:

PRIORITY 1: COMMUNITY SUPPORT
├── Welcome every new member
├── Answer every question <1 hour
├── Guide through verification
├── Encourage introductions
└── Facilitate first connections

PRIORITY 2: CONTENT
├── Post scheduled content
├── Feature first collectors
├── Share purchase announcements
├── Create FOMO through activity
└── Document organic moments

PRIORITY 3: MONITORING
├── Track sales metrics
├── Monitor community sentiment
├── Identify issues early
├── Document feedback
└── Celebrate milestones

PRIORITY 4: DOCUMENTATION
├── Screenshot first sales
├── Save testimonials
├── Record verification numbers
├── Track member growth
└── Note improvement areas

Deliverable: Established community momentum

## 📅 WEEKS 15-16: POST-LAUNCH ACTIVATION

Objective: Activate core features and establish operations [2]

### Task 15.1: Open Marriage Registry

| Field | Details |
| --- | --- |
| Duration | 2 hours |
| Priority | 🔴 Critical |
| Dependencies | Launch complete |

Specific Instructions:

REGISTRY OPENING:

1. Post announcement in #announcements:
   "📜 THE REGISTRY IS NOW OPEN!
   
   You can now marry physical artworks to your NFTs.
   
   Full guide: #registry-how-to
   
   First 5 marriages get featured!"

2. Pin guide in #marriage-requests

3. Monitor first submissions closely

4. Process within 48 hours

5. Create special feature post for first marriage

Deliverable: Active Marriage Registry

### Task 15.2: Facilitate First Trades

| Field | Details |
| --- | --- |
| Duration | Ongoing |
| Priority | 🟡 Important |
| Dependencies | Marketplace channels active |

Specific Instructions:

First Trade Activation:

ENCOURAGE TRADING:

1. Post in #announcements:
   "🏪 THE MARKETPLACE IS LIVE!
   
   Ready to list? Create a thread with [FS] tag.
   Looking to buy? Browse categories or post [WTB].
   
   Our first completed trade gets featured!"

2. Consider listing team-owned NFT to demonstrate

3. Monitor and guide first listings

4. Document first successful trade

5. Create content featuring first trade

6. Celebrate publicly

Deliverable: First successful community trade

### Task 15.3: Launch Philosophy Challenge

| Field | Details |
| --- | --- |
| Duration | 2 hours setup + weekly |
| Priority | 🟡 Important |
| Dependencies | Community established |

Specific Instructions:

Philosophy Challenge Structure: [2]

WEEKLY CHALLENGE FORMAT:

MONDAY: Challenge Announcement
├── Theme for the week
├── Prompt/question
├── Rules
├── Deadline (Saturday)
└── Prize (free Marriage fee)

MONDAY-FRIDAY: Submissions
├── Post in theme room
├── Tag with [CHALLENGE]
├── Community discussion

SATURDAY: Voting
├── Poll in Discord
├── Community votes
└── Winner announced

SUNDAY: Feature
├── Winner spotlighted
├── All participants thanked
├── Next challenge teased

WEEK 1 EXAMPLE:
Theme: Classical Foundations
Prompt: "Create art inspired by the concept of 'Know Thyself'"
Prize: Free Marriage verification

Deliverable: Running weekly Philosophy Challenge

### Task 15.4: Launch Transparency Systems [2]

| Field | Details |
| --- | --- |
| Duration | 4 hours |
| Priority | 🔴 Critical |
| Dependencies | Activity data |

Specific Instructions:

Trust Scoreboard Setup:

TRUST SCOREBOARD (Embed on website)

📦 TRADES COMPLETED        [count]
✅ SUCCESSFUL DELIVERY     [percentage]%
⚖️ DISPUTES RESOLVED       [count/count]
⏱️ AVG RESOLUTION TIME     [X] days
💍 MARRIAGES VERIFIED      [count]
⭐ TRUSTED SELLERS         [count]
👥 ACTIVE COMMUNITY        [count]

Last updated: [timestamp]

Provenance Museum Setup:

NOTION DATABASE:

Columns:
├── NFT Number (TM-001 through TM-448)
├── Title
├── Theme
├── Current Owner (wallet prefix)
├── Marriage Status
├── Transaction History
├── Price History
└── Dispute History

Make database publicly viewable
Embed on website as "The Living Ledger"

First Transparency Report:

TURBOMINDZ TRANSPARENCY REPORT
[Month Year]

📊 COMMUNITY
• Total Members: [X]
• New Members: [X]
• Active (7-day): [X]

💍 REGISTRY
• Marriage Requests: [X]
• Verified: [X]
• Pending: [X]

🏪 MARKETPLACE
• Listings Created: [X]
• Trades Completed: [X]
• Total Volume: $[X]

⚖️ DISPUTES
• Opened: [X]
• Resolved: [X]
• Avg Resolution: [X] days

💰 TREASURY
• Balance: [X] MATIC
• Revenue: [X]
• Expenses: [X]

Published: [Date]

Deliverable: Live Trust Scoreboard + First Transparency Report

# PHASE 4: OPERATIONS & GROWTH (Weeks 17-32)

## 📅 ONGOING WEEKLY OPERATIONS

Objective: Maintain sustainable production and community growth [2]

### Weekly Task Checklist

| Task | Time | Frequency | Owner |
| --- | --- | --- | --- |
| Quote research (14 quotes) | 4 hrs | Weekly | Curator |
| Art generation (14 NFTs) | 8 hrs | Weekly | Art Director |
| Metadata creation | 3 hrs | Weekly | Technical |
| IPFS upload & OpenSea listing | 2 hrs | Weekly | Technical |
| Instagram content (7 posts) | 3 hrs | Weekly | Marketing |
| Discord engagement | 7 hrs | Daily | Community |
| Marriage request processing | 2-4 hrs | As needed | Scribes |
| Transparency update | 1 hr | Weekly | Operations |

Daily Schedule Template:

IDEAL DAILY PRODUCTION (2 NFTs):

MORNING (2 hours):
├── 08:00-08:30: Quote selection from batch
├── 08:30-09:00: Concept extraction + prompt
├── 09:00-09:45: Generate + iterate
└── 09:45-10:00: Final selection

MIDDAY (1 hour):
├── 12:00-12:30: Metadata creation
└── 12:30-13:00: IPFS upload + verify

AFTERNOON (1 hour):
├── 14:00-14:30: OpenSea listing
└── 14:30-15:00: Social content creation

COMMUNITY (1 hour):
├── 16:00-16:30: Discord engagement
└── 16:30-17:00: Marriage processing

TOTAL: 5 focused hours/day

## 📅 MONTH 5 MILESTONES (Weeks 17-20)

Objective: Establish self-sustaining operations [2]

### Key Milestones:

□ First Elder Election (5 Elders via Snapshot)
□ 25+ completed physical trades
□ 500+ Discord members
□ First community governance vote
□ Guild Partnership #1 announced
□ First Analog Bridge gallery partnership
□ 100+ NFTs minted
□ 50+ Marriages completed

### Task 17.1: Elder Election

| Field | Details |
| --- | --- |
| Duration | 1 week process |
| Priority | 🔴 Critical |
| Dependencies | 100+ members |

Specific Instructions:

ELDER ELECTION PROCESS:

1. ANNOUNCEMENT (Day 1)
   Post in #governance:
   "📢 ELDER ELECTIONS NOW OPEN
   
   We're electing 5 Elders to serve as community 
   mediators and governance leaders.
   
   Eligibility:
   • Hold 1+ NFT
   • 3+ months membership
   • Good standing
   
   To nominate yourself or someone else, 
   reply to this thread."

2. NOMINATION PERIOD (Days 1-3)
   • Accept nominations
   • Nominees confirm acceptance
   • Each nominee posts platform statement

3. VOTING (Days 4-7)
   • Create Snapshot proposal
   • List all nominees
   • 1 NFT = 1 vote
   • Top 5 elected

4. RESULTS (Day 8)
   • Announce winners
   • Assign @Elder role
   • Brief on responsibilities
   • Welcome ceremony

Deliverable: 5 elected Elders serving community

### Task 17.2: Guild Partnerships [2]

| Field | Details |
| --- | --- |
| Duration | Ongoing outreach |
| Priority | 🟡 Important |
| Dependencies | Active marketplace |

Specific Instructions:

Partnership Target List:

CATEGORY: Paintings & Drawings
├── Target: Traditional art Discord servers
├── Approach: Cross-promotion offer
└── Contact: Server admins

CATEGORY: Photography
├── Target: NFT photography communities
├── Approach: Featured category partnership
└── Contact: Community leaders

CATEGORY: Digital Art
├── Target: AI art communities
├── Approach: Theme collaboration
└── Contact: Prominent creators

OUTREACH TEMPLATE:
"Hi [Name],

I'm from Turbomindz, a philosophical art NFT community 
with a unique marketplace organized by art medium.

We'd love to partner with [their community] for our 
[Category] section. Partnership includes:
• Featured community spotlight
• Cross-promotion
• Special [GUILD] tag for your members
• Exclusive theme discussion

Would you be open to a quick chat?

Best,
[Your name]"

Deliverable: 2+ guild partnerships established

## 📅 MONTH 6 MILESTONES (Weeks 21-24)

### Key Milestones:

□ 200+ NFTs minted
□ 100+ Marriages completed
□ @Trusted Seller program active
□ 4+ Guild Partnerships
□ Second art drop (if demand)
□ 6-month comprehensive report
□ Case study publication
□ Podcast/speaking appearance

## 📅 MONTHS 7-8 MILESTONES (Weeks 25-32)

### Key Milestones:

□ 350+ NFTs minted
□ Self-sustaining community operations
□ Ambassador program launched
□ Full governance activation
□ Multiple dispute resolutions documented
□ Year 2 roadmap developed
□ 448 NFTs complete (Week 32)
□ Comprehensive project review

# 📊 SUMMARY METRICS

## Task Count by Phase

| Phase | Weeks | Tasks | Hours |
| --- | --- | --- | --- |
| Foundation | 1-8 | 199 | ~100 |
| Pre-Launch | 9-12 | 150 | ~60 |
| Launch | 13-16 | 121 | ~80 |
| Operations | 17-32 | 240+ | ~320 |
| TOTAL | 32 | 710+ | 560+ |

## Critical Path Summary

Week 1: Quote research (100+) ─────────────┐
                                           │
Week 3-4: Generate 50 artworks ────────────┤
                                           │
Week 5: OpenSea + Discord setup ───────────┤
                                           │
Week 6: Guild.xyz token gating ────────────┤
                                           │
Week 7: Finalize Charter ──────────────────┤
                                           │
Week 8: Train Scribes, test systems ───────┤
                                           │
Week 9: Build website ─────────────────────┤
                                           │
Week 12: Build 200+ community ─────────────┤
                                           │
Week 14: ★ MINT LAUNCH ★ ──────────────────┘

## Production Totals

NFT PRODUCTION SCHEDULE:

Weeks 1-4:   50 NFTs (initial batch)
Weeks 5-14:  0 NFTs (infrastructure focus)
Weeks 15-32: 398 NFTs (14/week × 28.4 weeks)

TOTAL: 448 NFTs

Daily Rate: 2 NFTs/day (5 days/week)
Weekly Rate: 14 NFTs/week
Quote Research: Batch weekly (14 quotes)

# ✅ MASTER CHECKLIST

## Phase 1 Checklist (Weeks 1-8)

WEEK 1:
□ Register domain
□ Create treasury wallet
□ Research 100+ quotes
□ Draft legal documents

WEEK 2:
□ Define color palette
□ Select typography
□ Design logo
□ Create style guide
□ Design characters (Cosmo & Nova)

WEEK 3:
□ Define art style parameters
□ Create prompt templates
□ Generate first 25 artworks

WEEK 4:
□ Generate remaining 25 artworks
□ Set up Pinata IPFS
□ Create metadata JSON
□ Upload to IPFS

WEEK 5:
□ Create OpenSea collection
□ Mint 50 NFTs
□ Set up Discord
□ Configure forum tags

WEEK 6:
□ Set up Guild.xyz
□ Configure Snapshot
□ Create role structure

WEEK 7:
□ Finalize Charter
□ Create Marriage guide
□ Create Trading guide
□ Create FAQ

WEEK 8:
□ Recruit Scribes
□ Train Scribes
□ Run mock marriages
□ Run mock trades
□ Complete system test

## Phase 2 Checklist (Weeks 9-12)

WEEK 9:
□ Build website (Carrd)
□ Write all copy
□ Configure domain

WEEK 10:
□ Create social templates
□ Generate character graphics
□ Create 30-day content calendar

WEEK 11:
□ Set up social accounts
□ Launch content push
□ Begin daily posting

WEEK 12:
□ Soft open Discord
□ Host Twitter Space
□ Run whitelist campaign
□ Target: 200+ members

## Phase 3 Checklist (Weeks 13-16)

WEEK 13:
□ Final system verification
□ Team briefing
□ Content pre-scheduling
□ Rest before launch

WEEK 14:
□ 🚀 LAUNCH
□ Active support mode
□ Welcome all members
□ Document everything

WEEK 15:
□ Open Marriage Registry
□ Process first marriages
□ Facilitate first trades
□ Launch Philosophy Challenge

WEEK 16:
□ Launch Trust Scoreboard
□ Launch Provenance Museum
□ First transparency report
□ First member spotlights

## Phase 4 Checklist (Weeks 17-32)

ONGOING:
□ Weekly quote research (14)
□ Weekly art generation (14)
□ Weekly metadata + listings
□ Daily Discord engagement
□ Weekly transparency updates
□ Monthly comprehensive reports

MONTH 5:
□ First Elder election
□ 25+ trades completed
□ Guild Partnership #1
□ 500+ members

MONTH 6:
□ 100+ marriages
□ @Trusted Seller active
□ Case study published
□ 4+ partnerships

MONTHS 7-8:
□ Full governance active
□ Ambassador program
□ 448 NFTs complete
□ Year 2 planning

This task list provides a comprehensive production workflow for the Turbomindz NFT project. Each task includes specific instructions, time estimates, dependencies, and deliverables to enable consistent execution across all phases. The system is designed to support both human operators and AI agents in maintaining quality and meeting production targets.

Total Production: 448 NFTs over 32 weeks Daily Rate: 2 NFTs/day Weekly Operations: ~15-20 hours ongoing

CREATE. CONNECT. TRADE FAIR. 🎨🤝✨

### References

- 8 Steps to Create a Project Management Timeline | Lucidchart Blog. https://www.lucidchart.com

- How To Create a Project Timeline In 6 Simple Steps (with Templates). https://creately.com

- Task List – Free Timeline Templates. https://www.officetimeline.com

- How to Create a Project Timeline: Template and Examples [2025] • Asana. https://asana.com

- Project Timeline: How to Create, Manage, and Optimize. https://www.teamwork.com

- Project timeline: meet deadlines & hit milestones - Meister. https://www.meistertask.com

- Create and manage a project task list - Microsoft Support. https://support.microsoft.com

- Project Timeline Guide with Examples. https://www.projectmanager.com

- How to create a project timeline (with tips and examples) | Nulab. https://nulab.com

- Add tasks to the timeline - Microsoft Support. https://support.microsoft.com